## Sheet1
STREET | FROM | TO | STATUS_BEGIN | STATUS_END | Maintenance and Rehabilitation Strategy | Maintenance and Rehabilitation Activity
12TH STREET | CEDAR STREET | DEAD-END | February 01, 2021 | October 01, 2023 | Street Rehabilitation | Surf Recon + Base Rehab / FWM + Strctrl Ptch + Olay
14TH STREET | CEDAR STREET | DEAD-END | February 01, 2021 | October 01, 2023 | Street Rehabilitation | Surf Recon + Base Rehab / FWM + Strctrl Ptch + Olay
15TH STREET | CEDAR STREET | DEAD-END | February 01, 2021 | October 01, 2023 | Street Rehabilitation | Surf Recon + Base Rehab / FWM + Strctrl Ptch + Olay
ADA AVENUE | HAYWOOD DRIVE | COMSTOCK ROAD | March 01, 2022 | May 01, 2022 | Concrete Pavement Repair | PCC Moderate Pnl Rplcmnt (< 20%) + Grind
ANGELINA STREET | 13TH STREET | WEST END | February 01, 2021 | August 01, 2021 | Street Rehabilitation | Surf Recon + Base Rehab / FWM + Strctrl Ptch + Olay
Annie Lou Drive | Parkview Drive | South End | September 01, 2022 | April 01, 2023 | Pavement Preservation | EM/FWM + Moderate Overlay (2.0 - 3.0)
ARABELLA AVENUE | PENNSYLVANIA STREET | ATLANTA AVENUE | January 01, 2022 | September 01, 2022 | Street Rehabilitation | FWM + Thick Overlay (> 2.0 - 3.0) + Strctrl Ptch
Ashland Lane | Avenue Bellchase | End of Cul-De-Sac to the East | December 01, 2018 | November 01, 2019 | Concrete Pavement Repair | PCC Extensive Pnl Rplcmnt (<33%) + Grind
ATLANTA AVENUE | ARABELLA STREET | SOUTH END | January 01, 2022 | December 01, 2022 | Street Rehabilitation | ACP Full Depth Reconstruction
Auburn Drive | Baylor Lane | Cornell Drive | December 01, 2018 | January 01, 2021 | Concrete Pavement Repair | PCC Slight Pnl Rplcmnt (<10%) + Grind
AUGUSTA STREET | IRVING AVENUE | HIGHLAND AVENUE | January 01, 2022 | May 01, 2023 | Street Rehabilitation | FWM + Thick Overlay (> 2.0 - 3.0) + Strctrl Ptch
Austin Street | Driskill Street | IH-10 Frontage Road | December 01, 2018 | November 01, 2019 | Concrete Pavement Repair | PCC Moderate Pnl Rplcmnt (< 20%) + Grind
AVENUE B | COLLEGE STREET | BLANCHETTE STREET | January 01, 2022 | November 01, 2023 | Street Rehabilitation | FWM + Thick Overlay (> 2.0 - 3.0) + Strctrl Ptch
AVENUE E | ROYAL STREET | WASHINGTON BOULEVARD | January 01, 2022 | July 01, 2023 | Street Rehabilitation | Surf Recon + Base Rehab / FWM + Strctrl Ptch + Olay
AVENUE F | COLLEGE STREET | FRANKLIN STREET | January 01, 2022 | September 01, 2022 | Street Rehabilitation | FWM + Thick Overlay (> 2.0 - 3.0) + Strctrl Ptch
Baker Road | West End | East End | September 01, 2022 | March 01, 2023 | Pavement Preservation | Surf Recon + Base Rehab / FWM + Strctrl Ptch + Olay
BALDWIN STREET | CONCORD ROAD | RUSSELL DRIVE | March 01, 2022 | April 01, 2022 | Concrete Pavement Repair | PCC Extensive Pnl Rplcmnt (<33%) + Grind
Barrett Road | Roland Road | Bennett Road | March 01, 2019 | June 01, 2019 | Street Rehabilitation | Surf Recon + Base Rehab / FWM + Strctrl Ptch + Olay
BARTON STREET | REGINA LANE | EDSON DRIVE | March 01, 2022 | April 01, 2022 | Concrete Pavement Repair | PCC Localized Rehab
BEECH AVENUE | 9TH STREET | 10TH STREET | February 01, 2021 | 2023-03-01 | Street Rehabilitation | ACP Full Depth Reconstruction
BEECH AVENUE | CENTER STREET | FORRESTREET STREET | February 01, 2021 | September 01, 2022 | Street Rehabilitation | FWM + Thick Overlay (> 2.0 - 3.0) + Strctrl Ptch
BEECH AVENUE | IH-10 FRONTGAGE | CENTER STREET | February 01, 2021 | September 01, 2022 | Street Rehabilitation | FWM + Thick Overlay (> 2.0 - 3.0) + Strctrl Ptch
Bennett Road | Helbig Road | East End | March 01, 2019 | June 01, 2019 | Street Rehabilitation | FWM + Thick Overlay (> 2.0 - 3.0) + Strctrl Ptch
Berard Circle | Tyrrell Park Road | West End | September 01, 2022 | April 01, 2023 | Pavement Preservation | EM/FWM + Moderate Overlay (2.0 - 3.0)
Berkley Avenue | Trinidad Street | Parry Street | March 01, 2019 | September 01, 2020 | Street Rehabilitation | Edge Mill + Thin Overlay (1.5 - 2.0) + Strctrl Ptch
Berkshire Lane | North Caldwood Drive | Stratton Lane | December 01, 2018 | June 01, 2020 | Concrete Pavement Repair | PCC Slight Pnl Rplcmnt (<10%) + Grind
BESSEMER AVENUE | BUCHANAN STREET | TYLER STREET | January 01, 2022 | December 01, 2022 | Street Rehabilitation | ACP Full Depth Reconstruction
Blackmon Lane | Minglewood Drive | Willowood Drive | December 01, 2018 | August 01, 2020 | Street Rehabilitation | EM/FWM + Moderate Overlay (2.0 - 3.0)
BLOSSOM DRIVE | PROCTER STREET | PIERRE DRIVE | March 01, 2022 | September 01, 2022 | Concrete Pavement Repair | PCC Slight Pnl Rplcmnt (<10%) + Grind
BOB STREET | SARAH STREET | VIRGINIA STREET | April 01, 2021 | July 01, 2021 | CDBG Street Rehabilitation | Surf Recon + Base Rehab / FWM + Strctrl Ptch + Olay
BOB STREET | SARAH STREET | MAY STREET | April 01, 2021 | August 01, 2021 | CDBG Street Rehabilitation | Surf Recon + Base Rehab / FWM + Strctrl Ptch + Olay
Bonney Briar Place | Willow Way Drive | End of Cul-De-Sac | December 01, 2018 | February 01, 2020 | Concrete Pavement Repair | PCC Localized Rehab
Bordages Lane | North End | South End | September 01, 2022 | November 01, 2022 | Pavement Preservation | Edge Mill + Thin Overlay (1.5 - 2.0)
BRANDON AVENUE | HARRIOT STREET | LAVACA STREET | March 01, 2021 | June 01, 2021 | Street Rehabilitation | ACP Full Depth Reconstruction
BRANDON AVENUE | WOODROW AVENUE | CAMPUS STREET | March 01, 2021 | June 01, 2021 | Street Rehabilitation | ACP Full Depth Reconstruction
BRISTOL DRIVE | S 23RD STREET | CUL-DE-SAC | March 01, 2022 | November 01, 2022 | Concrete Pavement Repair | PCC Localized Rehab
Broad Oak Street | Eastex Freeway | Edgewater Drive | March 01, 2019 | February 01, 2020 | Street Rehabilitation | FWM + Thick Overlay (> 2.0 - 3.0)
BROUSSARD ROAD | TRAM ROAD | CITY LIMITS | January 01, 2022 | June 01, 2022 | Street Rehabilitation | Surf Recon + Base Rehab / FWM + Strctrl Ptch + Olay
BUCHANAN STREET | BETHLEHEM AVENUE | BESSEMER AVENUE | January 01, 2022 | December 01, 2022 | Street Rehabilitation | ACP Full Depth Reconstruction
Buchanan Street | Carnegie Street | Magnolia Avenue | September 01, 2022 | March 01, 2023 | Pavement Preservation | FWM + Thick Overlay (> 2.0 - 3.0) + Strctrl Ptch
Buchanan Street | Sheffield Avenue | West End | September 01, 2022 | March 01, 2023 | Pavement Preservation
Buffalo Street | East Lucas Drive | Wilson Street | September 01, 2022 | March 01, 2023 | Pavement Preservation | EM/FWM + Moderate Overlay (2.0 - 3.0)
Cambridge Lane | Berkshire Lane | Montclair Drive | December 01, 2018 | June 01, 2020 | Concrete Pavement Repair | PCC Localized Rehab
Candy Lane | Scenic Drive | North End | September 01, 2022 | November 01, 2022 | Pavement Preservation | Edge Mill + Thin Overlay (1.5 - 2.0)
CARLISLE DRIVE | CONCORD ROAD | FRENCH ROAD | March 01, 2021 | July 01, 2021 | Street Rehabilitation | Surf Recon + Base Rehab / FWM + Strctrl Ptch + Olay
Carnegie Street | North End | Buchanan Street | September 01, 2022 | March 01, 2023 | Pavement Preservation | FWM + Thick Overlay (> 2.0 - 3.0) + Strctrl Ptch
CARPENTER ROAD | Dead-End | PCT. 1 | February 01, 2021 | April 01, 2023 | Street Rehabilitation | FWM + Thick Overlay (> 2.0 - 3.0)
Carpenter Road | Oak Ridge Street | North End | September 01, 2022 | October 01, 2022 | Pavement Preservation | FWM + Thick Overlay (> 2.0 - 3.0)
Cash Circle | Berard Circle | North End | September 01, 2022 | April 01, 2023 | Pavement Preservation | EM/FWM + Moderate Overlay (2.0 - 3.0)
Chamberlin Drive | College Street | Washington Boulevard | March 01, 2019 | June 01, 2020 | Street Rehabilitation | FWM + Thick Overlay (> 2.0 - 3.0)
Chamberlin Drive | Maitland Street | College Street | March 01, 2019 | June 01, 2020 | Street Rehabilitation | FWM + Thick Overlay (> 2.0 - 3.0)
Chandler Drive | Downs Road | Dead End | September 01, 2022 | April 01, 2023 | Pavement Preservation | Slurry Seal / Seal Coat
Chapel Lane | Phelps Road | Seale Road | September 01, 2022 | April 01, 2023 | Pavement Preservation | Surf Recon + Base Rehab / FWM + Strctrl Ptch + Olay
CHERRY DRIVE | DOGWOOD LANE | SOUTH END | February 01, 2021 | September 01, 2022 | Street Rehabilitation | FWM + Thick Overlay (> 2.0 - 3.0) + Strctrl Ptch
CHURCH ROAD | BROUSSARD ROAD | SOUTH END | January 01, 2022 | May 01, 2022 | Street Rehabilitation | Surf Recon + Base Rehab / FWM + Strctrl Ptch + Olay
Clay Circle | Scenic Drive | East End | September 01, 2022 | November 01, 2022 | Pavement Preservation | Edge Mill + Thin Overlay (1.5 - 2.0)
Click Drive | East End | West End | September 01, 2022 | October 01, 2022 | Pavement Preservation | Edge Mill + Thin Overlay (1.5 - 2.0)
College Street | 300 FT West of 11th Street | 500 FT East of 11th Street | December 01, 2018 | March 01, 2019 | Concrete Pavement Repair | PCC Slight Pnl Rplcmnt (<10%)
Collier Road | Major Drive | Berry Road | September 01, 2022 | February 01, 2023 | Pavement Preservation | Slurry Seal / Seal Coat
Colonial Drive |  |  | December 01, 2018 | January 01, 2020 | Concrete Pavement Repair | PCC Localized Rehab
Combs Drive | Tyrrell Park Road | West End | September 01, 2022 | April 01, 2023 | Pavement Preservation | Surf Recon + Base Rehab / FWM + Strctrl Ptch + Olay
Continental/Ventura |  |  | December 01, 2018 | April 01, 2021 | Concrete Pavement Repair | PCC Jnt Rehab & Crk Seal
Corley Avenue | 12th Street | South 11th STREET | December 01, 2018 | November 01, 2020 | Concrete Pavement Repair | PCC Extensive Pnl Rplcmnt (<33%) + Grind
Corley Avenue | Ocean Drive | Rainbow | December 01, 2018 | April 01, 2021 | Concrete Pavement Repair | PCC Moderate Pnl Rplcmnt (< 20%) + Grind
Corley Avenue | South 9th Street | South 8th STREET | December 01, 2018 | March 01, 2021 | Concrete Pavement Repair | PCC Extensive Pnl Rplcmnt (<33%) + Grind
CORPORATE DRIVE | DIRECTOR | 69 FEEDER ROAD | February 01, 2021 | May 01, 2023 | Street Rehabilitation | Routine Maintenance
Crestwood Drive | Crawford Street | 19th STREET | December 01, 2018 | October 01, 2019 | Concrete Pavement Repair | PCC Slight Pnl Rplcmnt (<10%) + Grind
Daisy Drive | Norwood Drive | Elaine Drive | December 01, 2018 | January 01, 2020 | Concrete Pavement Repair | PCC Localized Rehab
Detroit Avenue | Wilson Street | Concord Road | September 01, 2022 | April 01, 2023 | Pavement Preservation | Edge Mill + Thin Overlay (1.5 - 2.0) + Strctrl Ptch
DISHMAN ROAD | MAJOR DRIVE | COUNTY MAINTENANCE SIGN | January 01, 2022 | June 01, 2022 | Street Rehabilitation | MicroSurface / Chip Seal
Doucette Avenue | Irving Avenue | Brooklyn Street | December 01, 2018 | March 01, 2021 | Concrete Pavement Repair | EM/FWM + Moderate Overlay (2.0 - 3.0) + Strctrl Ptch
DRENNAN DRIVE | MAJOR DRIVE | TROJAN ROAD | February 01, 2021 | June 01, 2023 | Street Rehabilitation | Surf Recon + Base Rehab / FWM + Strctrl Ptch + Olay
Drexell Drive | Scenic Drive | North End | September 01, 2022 | November 01, 2022 | Pavement Preservation | Edge Mill + Thin Overlay (1.5 - 2.0)
DRISKILL STREET | KENWOOD DRIVE | AUSTIN STREET | March 01, 2022 | April 01, 2022 | Concrete Pavement Repair | PCC Slight Pnl Rplcmnt (<10%) + Grind
DUFF STREET | JAY DRIVE | YOUNT STREET | January 01, 2022 | August 01, 2023 | Street Rehabilitation | Surf Recon + Base Rehab / FWM + Strctrl Ptch + Olay
E. LAVACA STREET | RAILROAD TRACK | HIGHLAND AVENUE | March 01, 2022 | October 01, 2022 | Concrete Pavement Repair | PCC Slight Pnl Rplcmnt (<10%) + Grind
East Circuit Drive | N. Circuit Drive | Calder Avenue | March 01, 2019 | September 01, 2019 | Street Rehabilitation | Edge Mill + Thin Overlay (1.5 - 2.0) + Strctrl Ptch
East Lavaca Street | Hartel Street | University Drive | December 01, 2018 | April 01, 2019 | Concrete Pavement Repair | PCC Slight Pnl Rplcmnt (<10%) + Grind
East Lavaca Street | Highland Avenue | Spark Street | December 01, 2018 | April 01, 2019 | Concrete Pavement Repair | PCC Slight Pnl Rplcmnt (<10%) + Grind
ECTOR AVENUE | HARRIOT STREET | SOUTH END | April 01, 2021 | July 01, 2021 | Street Rehabilitation | ACP Full Depth Reconstruction
EDMONDS AVENUE | S 5TH STREET | GOLIAD STREET | January 01, 2022 | May 01, 2023 | Street Rehabilitation | Surf Recon + Base Rehab / FWM + Strctrl Ptch + Olay
Edson Drive | Gladys Avenue | N. Circuit Drive | March 01, 2019 | September 01, 2019 | Street Rehabilitation | Routine Maintenance
Edson Drive | Gladys Avenue | North Circuit Drive | December 01, 2018 | August 01, 2019 | Concrete Pavement Repair | Routine Maintenance
Elaine Drive | Daisy Drive | Westgate Drive | December 01, 2018 | December 01, 2019 | Concrete Pavement Repair | PCC Jnt Rehab & Crk Seal
Eldridge Drive | McLean Drive | South End | March 01, 2019 | August 01, 2019 | Street Rehabilitation | FWM + Thick Overlay (> 2.0 - 3.0)
ELGIE STREET | AVENUE E | AVENUE C | February 01, 2021 | March 01, 2023 | Street Rehabilitation | FWM + Thick Overlay (> 2.0 - 3.0) + Strctrl Ptch
ELGIE STREET | AVENUE C | EAST END | February 01, 2021 | March 01, 2023 | Street Rehabilitation | FWM + Thick Overlay (> 2.0 - 3.0) + Strctrl Ptch
ELGIE STREET | WEST END | AVENUE E | February 01, 2021 | March 01, 2023 | Street Rehabilitation | FWM + Thick Overlay (> 2.0 - 3.0) + Strctrl Ptch
Elinor Street | Iola Street | Donahue Street | March 01, 2019 | October 01, 2019 | Street Rehabilitation | FWM + Thick Overlay (> 2.0 - 3.0)
Elmhurst Drive | Tara Street | End of Cul-De-Sac to the East | December 01, 2018 | November 01, 2019 | Concrete Pavement Repair | PCC Localized Rehab
Emerald Drive | Tyrrell Park Road | West End | September 01, 2022 | April 01, 2023 | Pavement Preservation | Surf Recon + Base Rehab / FWM + Strctrl Ptch + Olay
EMMETT AVENUE | BLANCHETTE STREET | LAND STREET | February 01, 2021 | May 01, 2021 | Street Rehabilitation | ACP Full Depth Reconstruction
EMMETT AVENUE | GRAY STREET | NECHES STREET | February 01, 2021 | May 01, 2021 | Street Rehabilitation | ACP Full Depth Reconstruction
EMMETT AVENUE | LAND STREET | GRAY STREET | February 01, 2021 | May 01, 2021 | Street Rehabilitation | ACP Full Depth Reconstruction
EMMETT AVENUE | PARK STREET | NECHES STREET | February 01, 2021 | February 01, 2021 | Street Rehabilitation | FWM + Thick Overlay (> 2.0 - 3.0) + Strctrl Ptch
Ethel Street | Elinor Stret | Fannett Road | March 01, 2019 | October 01, 2019 | Street Rehabilitation | FWM + Thick Overlay (> 2.0 - 3.0)
EUCLID STREET | WEST END | IOLA STREET | March 01, 2021 | April 01, 2021 | Street Rehabilitation | ACP Full Depth Reconstruction
Fairway Street | Magnolia Avenue | Osborn Street | March 01, 2019 | March 01, 2020 | Street Rehabilitation | FWM + Thick Overlay (> 2.0 - 3.0)
Folsom Drive | Ridgeland Avenue | West Lucas | December 01, 2018 | March 01, 2019 | Concrete Pavement Repair | PCC Slight Pnl Rplcmnt (<10%) + Grind
GARDEN STREET | HEBERT STREET | LELA STREET | January 01, 2022 | May 01, 2023 | Street Rehabilitation | ACP Full Depth Reconstruction
General Drive | Trinidad Road | South End | September 01, 2022 | March 01, 2023 | Pavement Preservation | Edge Mill + Thin Overlay (1.5 - 2.0)
Georgetown Street | Townhouse Lane | Meadow Way | December 01, 2018 | May 01, 2020 | Concrete Pavement Repair | PCC Moderate Pnl Rplcmnt (< 20%) + Grind
Gerald Drive | Wescalder Road | Katy Drive | September 01, 2022 | March 01, 2023 | Pavement Preservation | Edge Mill + Thin Overlay (1.5 - 2.0) + Strctrl Ptch
GLASGOW LANE | HOWELL STREET | CUL-DE-SAC | March 01, 2022 | April 01, 2022 | Concrete Pavement Repair | PCC Localized Rehab
GLEN OAKS CIRCLE | COMSTOCK ROAD | CUL-DE-SAC | March 01, 2022 | May 01, 2022 | Concrete Pavement Repair | Routine Maintenance
GLENDALE STREET | COLLEGE STREET | PEVITOT STREET | January 01, 2022 | October 01, 2022 | Street Rehabilitation | Edge Mill + Thin Overlay (1.5 - 2.0)
GLENWOOD AVENUE | 11TH STREET | FANNETT ROAD | March 01, 2021 | April 01, 2021 | Street Rehabilitation | FWM + Thick Overlay (> 2.0 - 3.0) + Strctrl Ptch
GLENWOOD AVENUE | S 5TH STREET | GOLIAD STREET | January 01, 2022 | May 01, 2023 | Street Rehabilitation | Surf Recon + Base Rehab / FWM + Strctrl Ptch + Olay
GOLIAD STREET | COLLEGE STREET | WASHINGTON BOULEVARD | April 01, 2021 | July 01, 2021 | Street Rehabilitation | Surf Recon + Base Rehab / FWM + Strctrl Ptch + Olay
GOLIAD STREET | WASHINGTON BOULEVARD | W. VIRGINIA STREET | January 01, 2022 | May 01, 2023 | Street Rehabilitation | FWM + Thick Overlay (> 2.0 - 3.0) + Strctrl Ptch
Grant Street | Brooklyn Street | Poplar Street | December 01, 2018 | January 01, 2021 | Concrete Pavement Repair | PCC Slight Pnl Rplcmnt (<10%) + Grind
GRAY STREET | BLANCHETTE STREET | EMMETT AVENUE | February 01, 2021 | April 01, 2021 | Street Rehabilitation | ACP Full Depth Reconstruction
GRAY STREET | EMMETT AVENUE | LANGHAM STREET | February 01, 2021 | April 01, 2021 | Street Rehabilitation | ACP Full Depth Reconstruction
Greeves Avenue | Mclean Drive | Landis Drive | September 01, 2022 | November 01, 2022 | Pavement Preservation | Edge Mill + Thin Overlay (1.5 - 2.0)
Harriot Street | Avenue B | Avenue C | March 01, 2019 | October 01, 2019 | Street Rehabilitation | FWM + Thick Overlay (> 2.0 - 3.0)
HARRIOT STREET | FANNETT ROAD | WACO STREET | January 01, 2022 | May 01, 2023 | Street Rehabilitation | FWM + Thick Overlay (> 2.0 - 3.0) + Strctrl Ptch
Hayes Lane | Harding Drive | Steelton Street | September 01, 2022 | March 01, 2023 | Pavement Preservation | MicroSurface / Chip Seal + Strctrl Ptch
HAYWOOD DRIVE | CONCORD ROAD | ADA AVENUE | March 01, 2022 | May 01, 2022 | Concrete Pavement Repair | PCC Localized Rehab
HEATHERWOOD DRIVE | FOLSOM DRIVE | CUL-DE-SAC | March 01, 2022 | April 01, 2022 | Concrete Pavement Repair | PCC Localized Rehab
Hebert Street | Houston Street | West End | March 01, 2019 | January 01, 2020 | Street Rehabilitation | FWM + Thick Overlay (> 2.0 - 3.0) + Strctrl Ptch
HEGELE STREET | GOLIAD STREET | WACO STREET | January 01, 2022 | May 01, 2023 | Street Rehabilitation | FWM + Thick Overlay (> 2.0 - 3.0) + Strctrl Ptch
HELBIG ROAD | LUCAS DRIVE | ASPHALT PAVEMENT | March 01, 2022 | June 01, 2022 | Concrete Pavement Repair | EM/FWM + Moderate Overlay (2.0 - 3.0)
HILLCREST DRIVE | BROUSSARD ROAD | NORTH END | January 01, 2022 | May 01, 2022 | Street Rehabilitation | Surf Recon + Base Rehab / FWM + Strctrl Ptch + Olay
HODGE ROAD | BROUSSARD ROAD | SOUTH END | January 01, 2022 | May 01, 2022 | Street Rehabilitation | Edge Mill + Thin Overlay (1.5 - 2.0)
HOLTON STREET | HUMBLE ROAD | BAKER ROAD | February 01, 2021 | July 01, 2021 | Street Rehabilitation | Surf Recon + Base Rehab / FWM + Strctrl Ptch + Olay
HOOKS AVENUE | JAY DRIVE | YOUNT STREET | January 01, 2022 | August 01, 2023 | Street Rehabilitation | FWM + Thick Overlay (> 2.0 - 3.0) + Strctrl Ptch
Houston Street | Ollie Street | Hebert Street | December 01, 2018 | December 01, 2020 | Concrete Pavement Repair | PCC Moderate Pnl Rplcmnt (< 20%) + Grind
HOUSTON STREET | SARAH STREET | SOUTH END | February 01, 2021 | April 01, 2023 | Street Rehabilitation | Surf Recon + Base Rehab / FWM + Strctrl Ptch + Olay
Humble Road | Wescalder Road | Major Drive | September 01, 2022 | March 01, 2023 | Pavement Preservation | Edge Mill + Thin Overlay (1.5 - 2.0)
Hurley Drive | Old Voth Road | West End | September 01, 2022 | November 01, 2022 | Pavement Preservation | EM/FWM + Moderate Overlay (2.0 - 3.0) + Strctrl Ptch
Infinity Lane | Serene Drive | Dellwood Lane | December 01, 2018 | August 01, 2019 | Concrete Pavement Repair | PCC Localized Rehab
Iola Street | Washington Boulevard | St. James Boulevard | March 01, 2019 | October 01, 2019 | Street Rehabilitation | FWM + Thick Overlay (> 2.0 - 3.0)
IRVING AVENUE | HIGHLAND DRIVE | FLORIDA AVENUE | January 01, 2022 | May 01, 2023 | Street Rehabilitation | FWM + Thick Overlay (> 2.0 - 3.0) + Strctrl Ptch
ISLA AVENUE | M L KING PARKWAY | DEXTER STREET | February 01, 2021 | September 01, 2021 | Street Rehabilitation | Surf Recon + Base Rehab / FWM + Strctrl Ptch + Olay
Jamestown Street | Oak Ridge Street | Pine Ridge Drive | September 01, 2022 | October 01, 2022 | Pavement Preservation | Edge Mill + Thin Overlay (1.5 - 2.0)
JAY DRIVE | HOOKS AVENUE | KOHLER STREET | January 01, 2022 | September 01, 2023 | Street Rehabilitation | FWM + Thick Overlay (> 2.0 - 3.0) + Strctrl Ptch
Jean Drive | Wescalder Road | Katy Drive | September 01, 2022 | March 01, 2023 | Pavement Preservation | Edge Mill + Thin Overlay (1.5 - 2.0) + Strctrl Ptch
Jim Gilligan Way | Hunter Street | MLK Jr Parkway | December 01, 2018 | July 01, 2019 | Concrete Pavement Repair | PCC Slight Pnl Rplcmnt (<10%) + Grind
Jim Gilligan Way | University Drive | Rolfe Christopher Drive | December 01, 2018 | February 01, 2019 | Concrete Pavement Repair | PCC Moderate Pnl Rplcmnt (< 20%) + Grind
Joesam Lane | Scenic Drive | North End | September 01, 2022 | November 01, 2022 | Pavement Preservation | Edge Mill + Thin Overlay (1.5 - 2.0)
Katy Drive | Moses Drive | Jean Drive | September 01, 2022 | March 01, 2023 | Pavement Preservation | Edge Mill + Thin Overlay (1.5 - 2.0) + Strctrl Ptch
KENNEDY DRIVE | NORTH END | PHELAN BOULEVARD | January 01, 2022 | September 01, 2023 | Street Rehabilitation | FWM + Thick Overlay (> 2.0 - 3.0) + Strctrl Ptch
Kenwood Drive | 300 West of Longfellow Drive | Longfellow Drive | December 01, 2018 | October 01, 2019 | Concrete Pavement Repair | PCC Slight Pnl Rplcmnt (<10%) + Grind
KOHLER STREET | JAY DRIVE | YOUNT STREET | January 01, 2022 | August 01, 2023 | Street Rehabilitation | EM/FWM + Moderate Overlay (2.0 - 3.0) + Strctrl Ptch
Lakeview Circle | Delaware Street | End of Cul-De-Sac | December 01, 2018 | July 01, 2020 | Concrete Pavement Repair | PCC Localized Rehab
Landis Drive | Greeves Avenue | Enfield Lane | September 01, 2022 | November 01, 2022 | Pavement Preservation | FWM + Thick Overlay (> 2.0 - 3.0) + Strctrl Ptch
LANDIS DRIVE | MAJOR DRIVE | ENFIELD LANE | January 01, 2022 | June 01, 2022 | Street Rehabilitation | FWM + Thick Overlay (> 2.0 - 3.0) + Strctrl Ptch
LANGHAM STREET | PARK STREET | PENNSYLVANIA AVENUE | February 01, 2021 | March 01, 2023 | Street Rehabilitation | FWM + Thick Overlay (> 2.0 - 3.0) + Strctrl Ptch
LAUREL AVENUE | 23RD STREET | OFFICE PARK DRIVE | March 01, 2022 | July 01, 2022 | Concrete Pavement Repair | PCC Moderate Pnl Rplcmnt (< 20%) + Grind
LAUREL AVENUE | PARK STREET | ORLEANS STREET | March 01, 2022 | June 01, 2022 | Concrete Pavement Repair | Routine Maintenance
Laverna Drive | Parkview Drive | South End | September 01, 2022 | April 01, 2023 | Pavement Preservation | EM/FWM + Moderate Overlay (2.0 - 3.0)
LEE STREET | POPLAR STREET | DEAD-END | February 01, 2021 | July 01, 2021 | Concrete Pavement Repair | ACP Full Depth Reconstruction
LELA STREET | PRADICE STREET | USAN STREET | January 01, 2022 | May 01, 2023 | Street Rehabilitation | FWM + Thick Overlay (> 2.0 - 3.0) + Strctrl Ptch
LEON STREET | GOLIAD STREET | PRESTON STREET | January 01, 2022 | May 01, 2023 | Street Rehabilitation | FWM + Thick Overlay (> 2.0 - 3.0) + Strctrl Ptch
Lewis Drive | Old Voth Road | West End | September 01, 2022 | October 01, 2022 | Pavement Preservation | MicroSurface / Chip Seal
LIBERTY AVENUE | 7TH STREET | 8TH STREET | March 01, 2022 | September 01, 2022 | Concrete Pavement Repair | PCC Jnt Rehab & Crk Seal
Lindbergh Drive | College Street | Jeny Lane | December 01, 2018 | June 01, 2020 | Concrete Pavement Repair | PCC Localized Rehab
LOLA LANE | RUTH ROAD | MORROGH DRIVE | March 01, 2022 | June 01, 2022 | Concrete Pavement Repair | PCC Slight Pnl Rplcmnt (<10%) + Grind
Longfellow Drive | Gladys Avenue | Kenwood Drive | December 01, 2018 | September 01, 2019 | Concrete Pavement Repair | PCC Moderate Pnl Rplcmnt (< 20%) + Grind
LOOP ROAD | BROUSSARD ROAD | 1250-FT NE OF | January 01, 2022 | April 01, 2022 | Street Rehabilitation | FWM + Thick Overlay (> 2.0 - 3.0)
LORELOCK LANE | FRENCH ROAD | REDWOOD DRIVE | February 01, 2021 | April 01, 2021 | Street Rehabilitation | FWM + Thick Overlay (> 2.0 - 3.0) + Strctrl Ptch
LUCILLE STREET | BOB STREET | EAST END | February 01, 2021 | November 01, 2021 | Street Rehabilitation | Surf Recon + Base Rehab / FWM + Strctrl Ptch + Olay
MADDOX STREET | E. VIRGINIA STREET | FLORIDA AVENUE | March 01, 2021 | June 01, 2021 | Street Rehabilitation | Surf Recon + Base Rehab / FWM + Strctrl Ptch + Olay
Maida Road | Helbig Road | East End | March 01, 2019 | June 01, 2019 | Street Rehabilitation | Routine Maintenance
Margo Lane | Beaumont Drive | 500 FT East of BMT Drive | December 01, 2018 | October 01, 2020 | Concrete Pavement Repair | MicroSurface / Chip Seal + Strctrl Ptch
MAYHAW DRIVE | AVIE LANE | ADA AVENUE | March 01, 2022 | May 01, 2022 | Concrete Pavement Repair | PCC Moderate Pnl Rplcmnt (< 20%) + Grind
McLean Drive | Major Drive | Armstrong Drive | March 01, 2019 | August 01, 2019 | Street Rehabilitation | FWM + Thick Overlay (> 2.0 - 3.0)
Mclean Drive | Major Drive | Greeves Avenue | September 01, 2022 | November 01, 2022 | Pavement Preservation | Edge Mill + Thin Overlay (1.5 - 2.0)
Meadow Way | Longmeadow Drive | Georgetown Street | December 01, 2018 | May 01, 2020 | Concrete Pavement Repair | PCC Moderate Pnl Rplcmnt (< 20%) + Grind
Mel Sha Lane | Seale Road | Roberts Road | September 01, 2022 | April 01, 2023 | Pavement Preservation | FWM + Thick Overlay (> 2.0 - 3.0)
MITCHELL ROAD | LOOP ROAD | SOUTHEAST END | January 01, 2022 | April 01, 2022 | Street Rehabilitation | MicroSurface / Chip Seal
MORROGH DRIVE | BAYOU ROAD | LOLA LANE | March 01, 2022 | July 01, 2022 | Concrete Pavement Repair | PCC Slight Pnl Rplcmnt (<10%) + Grind
Moses Drive | Wescalder Road | Katy Drive | September 01, 2022 | March 01, 2023 | Pavement Preservation | Edge Mill + Thin Overlay (1.5 - 2.0) + Strctrl Ptch
NELSON STREET | SOUTHERLAND STREET | HEGELE STREET | January 01, 2022 | May 01, 2023 | Street Rehabilitation | ACP Full Depth Reconstruction
NORA STREET | PRADICE STREET | LOU STREET | January 01, 2022 | May 01, 2023 | Street Rehabilitation | Surf Recon + Base Rehab / FWM + Strctrl Ptch + Olay
NORRIS STREET | HUMBLE ROAD | BAKER ROAD | February 01, 2021 | April 01, 2023 | Street Rehabilitation | Surf Recon + Base Rehab / FWM + Strctrl Ptch + Olay
North 23rd Street | Gladys Avenue | Queens Row | December 01, 2018 | July 01, 2019 | Concrete Pavement Repair | PCC Slight Pnl Rplcmnt (<10%) + Grind
Norwood Drive | Madrid Drive | Daisy Drive | December 01, 2018 | January 01, 2020 | Concrete Pavement Repair | Routine Maintenance
Oak Ridge Street | Loop Road | Carpenter Road | September 01, 2022 | October 01, 2022 | Pavement Preservation | FWM + Thick Overlay (> 2.0 - 3.0)
Oriole Drive | Wren Way | 300 FT East of Wren Way | December 01, 2018 | February 01, 2020 | Concrete Pavement Repair | PCC Moderate Pnl Rplcmnt (< 20%) + Grind
PALESTINE STREET | WASHINGTON BLVD | ROCKWELL STREET | February 01, 2021 | March 01, 2023 | Street Rehabilitation | FWM + Thick Overlay (> 2.0 - 3.0) + Strctrl Ptch
Pan Street | Futura Street | Belvedere Drive | December 01, 2018 | June 01, 2019 | Concrete Pavement Repair | PCC Jnt Rehab & Crk Seal
Parkview Drive | Fannett Road | Tyrrell Park Road | September 01, 2022 | April 01, 2023 | Pavement Preservation | EM/FWM + Moderate Overlay (2.0 - 3.0)
Parry Street | Magnolia Avenue | Beverly Avenue | March 01, 2019 | September 01, 2020 | Street Rehabilitation | FWM + Thick Overlay (> 2.0 - 3.0)
Parry Street | Osborn Street | Coleman Street | March 01, 2019 | September 01, 2020 | Street Rehabilitation | FWM + Thick Overlay (> 2.0 - 3.0)
Patricia Drive | Broussard Road | South End | September 01, 2022 | October 01, 2022 | Pavement Preservation | Edge Mill + Thin Overlay (1.5 - 2.0)
PECOS STREET | 13TH STREET | WEST END | February 01, 2021 | September 01, 2021 | Street Rehabilitation | Surf Recon + Base Rehab / FWM + Strctrl Ptch + Olay
PENNSYLVANIA STREET | ARABELLA STREET | WASHINGTON BOULEVARD | January 01, 2022 | November 01, 2023 | Street Rehabilitation | FWM + Thick Overlay (> 2.0 - 3.0) + Strctrl Ptch
PHELAN BOULEVARD | OFFICE PARK DRIVE | 300 FT WEST | March 01, 2022 | November 01, 2022 | Concrete Pavement Repair | PCC Moderate Pnl Rplcmnt (< 20%) + Grind
Phelan Boulevard | Plaza Drive | Peyton Drive | December 01, 2018 | March 01, 2019 | Concrete Pavement Repair | PCC Moderate Pnl Rplcmnt (< 20%) + Grind
PIERRE DRIVE | BLOSSOM DRIVE | CUL-DE-SAC | March 01, 2022 | September 01, 2022 | Concrete Pavement Repair | PCC Slight Pnl Rplcmnt (<10%) + Grind
Pinchback Street | Calder Avenue | College Street | March 01, 2019 | October 01, 2020 | Street Rehabilitation | Edge Mill + Thin Overlay (1.5 - 2.0)
Pine Burr Boulevard | Concord Road | Spencer Road | March 01, 2019 | April 01, 2020 | Street Rehabilitation | FWM + Thick Overlay (> 2.0 - 3.0)
Pine Ridge Drive | Jamestown Street | West End | September 01, 2022 | October 01, 2022 | Pavement Preservation | Edge Mill + Thin Overlay (1.5 - 2.0)
Pleasant Bend Drive | San Anselmo Street | Enchanted Avenue | December 01, 2018 | April 01, 2021 | Concrete Pavement Repair | PCC Localized Rehab
PRESTON STREET | POTTS STREET | HEBERT STREET | January 01, 2022 | March 01, 2023 | Street Rehabilitation | ACP Full Depth Reconstruction
Regina Lane | Cofey Drive | Edson Drive | December 01, 2018 | October 01, 2019 | Concrete Pavement Repair | Edge Mill + Thin Overlay (1.5 - 2.0)
Rena Street | Bob Street | Caddilac Lane | December 01, 2018 | April 01, 2019 | Concrete Pavement Repair | PCC Slight Pnl Rplcmnt (<10%) + Grind
Ridgeland Avenue | N. Circuit Drive | Calder Avenue | March 01, 2019 | August 01, 2019 | Street Rehabilitation | FWM + Thick Overlay (> 2.0 - 3.0) + Strctrl Ptch
Roberts Road | Tyrrell Park Road | Mel Sha Lane | September 01, 2022 | April 01, 2023 | Pavement Preservation | EM/FWM + Moderate Overlay (2.0 - 3.0) + Strctrl Ptch
ROBERTS STREET | VICTORIA STREET | SABINE PASS AVENUE | January 01, 2022 | February 01, 2023 | Street Rehabilitation | Surf Recon + Base Rehab / FWM + Strctrl Ptch + Olay
Roland Road | Speer Road | 800ft West of LeBlanc Road | March 01, 2019 | June 01, 2019 | Street Rehabilitation | MicroSurface / Chip Seal
Russell Drive | Concord Road | Baldwin Street | December 01, 2018 | June 01, 2020 | Concrete Pavement Repair | PCC Extensive Pnl Rplcmnt (<33%) + Grind
RUTH ROAD | BAYOU ROAD | ELOISE STREET | March 01, 2022 | July 01, 2022 | Concrete Pavement Repair | PCC Slight Pnl Rplcmnt (<10%) + Grind
S 5TH STREET | GLENWOOD AVENUE | HEBERT STREET | January 01, 2022 | May 01, 2023 | Street Rehabilitation | ACP Full Depth Reconstruction
SABINE PASS AVENUE | 137-FT N OF CARTWRIGHT AVENUE | WASHINGTON BOULEVARD | January 01, 2022 | November 01, 2023 | Street Rehabilitation | Surf Recon + Base Rehab / FWM + Strctrl Ptch + Olay
SANDLIN STREET | HUMBLE ROAD | BAKER ROAD | February 01, 2021 | April 01, 2023 | Street Rehabilitation | Surf Recon + Base Rehab / FWM + Strctrl Ptch + Olay
Sandwood Lane | Kenwood Drive | Crestwood Drive | December 01, 2018 | September 01, 2019 | Concrete Pavement Repair | PCC Localized Rehab + Grind
SARAH STREET | 4TH STREET | RAILROAD TRACK | March 01, 2022 | October 01, 2022 | Concrete Pavement Repair | PCC Slight Pnl Rplcmnt (<10%) + Grind
Scenic Drive | Major Drive | Highway 105 | September 01, 2022 | November 01, 2022 | Pavement Preservation | Edge Mill + Thin Overlay (1.5 - 2.0)
Scotts Drive | Old Voth Road | West End | September 01, 2022 | October 01, 2022 | Pavement Preservation | EM/FWM + Moderate Overlay (2.0 - 3.0) + Strctrl Ptch
Seale Road | Fannett Road | Tyrrell Park Road | September 01, 2022 | April 01, 2023 | Pavement Preservation | Edge Mill + Thin Overlay (1.5 - 2.0)
SHADY LANE | WHEAT DRIVE | SLEEPY LANE | March 01, 2022 | March 01, 2022 | Concrete Pavement Repair | PCC Moderate Pnl Rplcmnt (< 20%) + Grind
Sheffield Avenue | Wilson Street | South End | September 01, 2022 | March 01, 2023 | Pavement Preservation | MicroSurface / Chip Seal
Sherman Street | Hemlock Street | Carroll Street | December 01, 2018 | January 01, 2021 | Concrete Pavement Repair | PCC Slight Pnl Rplcmnt (<10%) + Grind
SMART STREET | 13TH STREET | WEST END | February 01, 2021 | August 01, 2021 | Street Rehabilitation
South 4th Street | Hebert Street | Nora Street | December 01, 2018 | May 01, 2019 | Concrete Pavement Repair | PCC Moderate Pnl Rplcmnt (< 20%) + Grind
SPACE STREET | CAMBELL STREET | EAST END | February 01, 2021 | February 01, 2022 | Street Rehabilitation | Surf Recon + Base Rehab / FWM + Strctrl Ptch + Olay
ST. CHARLES | FORREST | CABLE STREET | February 01, 2021 | September 01, 2022 | Street Rehabilitation | Slurry Seal / Seal Coat
St. James Boulevard | 11th Stret | Fannett Road | March 01, 2019 | September 01, 2019 | Street Rehabilitation | ACP Full Depth Reconstruction
STACEWOOD DRIVE | WESTGATE DRIVE | MADRID DRIVE | March 01, 2022 | August 01, 2022 | Concrete Pavement Repair | Routine Maintenance
SUNBURY DRIVE | E. CALDWOOD DRIVE | 150' WEST OF ROSINE STREET | March 01, 2021 | September 01, 2021 | Street Rehabilitation | Edge Mill + Thin Overlay (1.5 - 2.0) + Strctrl Ptch
Swift Drive | Trinidad Road | South End | September 01, 2022 | March 01, 2023 | Pavement Preservation | Surf Recon + Base Rehab / FWM + Strctrl Ptch + Olay
Swing Drive | Trinidad Road | South End | September 01, 2022 | March 01, 2023 | Pavement Preservation | Surf Recon + Base Rehab / FWM + Strctrl Ptch + Olay
Tara Street | Chadwick Drive | Dunleith Street | December 01, 2018 | November 01, 2019 | Concrete Pavement Repair | PCC Localized Rehab
Taylor Street | Ironton Avenue | Magnolia Avenue | September 01, 2022 | March 01, 2023 | Pavement Preservation | Edge Mill + Thin Overlay (1.5 - 2.0)
TERRELL AVENUE | SABINE PASS AVENUE | EAST END | January 01, 2022 | September 01, 2022 | Street Rehabilitation | ACP Full Depth Reconstruction
Thomas Court | Thomas Road | Dead End to the East | December 01, 2018 | November 01, 2019 | Concrete Pavement Repair | PCC Slight Pnl Rplcmnt (<10%) + Grind
THREADNEEDLE STREET | AVENUE E | AVENUE C | February 01, 2021 | March 01, 2023 | Street Rehabilitation | FWM + Thick Overlay (> 2.0 - 3.0)
THREADNEEDLE STREET | AVENUE C | EAST END | February 01, 2021 | March 01, 2023 | Street Rehabilitation | FWM + Thick Overlay (> 2.0 - 3.0)
THREADNEEDLE STREET | WEST END | AVENUE E | February 01, 2021 | March 01, 2023 | Street Rehabilitation | FWM + Thick Overlay (> 2.0 - 3.0)
TOLEDO STREET | CLEVELAND STREET | RENAUD STREET | February 01, 2021 | July 01, 2023 | Street Rehabilitation | EM/FWM + Moderate Overlay (2.0 - 3.0)
Townhouse Lane | Langham Road | Longmeadow Drive | December 01, 2018 | May 01, 2020 | Concrete Pavement Repair | PCC Moderate Pnl Rplcmnt (< 20%) + Grind
TROJAN ROAD | MCLEAN STREET | DRENNAN DRIVE | February 01, 2021 | June 01, 2023 | Street Rehabilitation | EM/FWM + Moderate Overlay (2.0 - 3.0) + Strctrl Ptch
TUPELO STREET | MAYHAW DRIVE | YAUPON DRIVE | March 01, 2022 | May 01, 2022 | Concrete Pavement Repair | PCC Jnt Rehab & Crk Seal
Turnberry Circle | Willow Bend Drive | East to the End of Cul-De-Sac | December 01, 2018 | March 01, 2020 | Concrete Pavement Repair | Routine Maintenance
Usan Street | Hebert Street | Nora Street | December 01, 2018 | December 01, 2020 | Concrete Pavement Repair | PCC Moderate Pnl Rplcmnt (< 20%) + Grind
Waco Street | Roberts Street | Washington Boulevard | March 01, 2019 | November 01, 2019 | Street Rehabilitation | FWM + Thick Overlay (> 2.0 - 3.0)
Waco Street | Washington Boulevard | Hebert Street | March 01, 2019 | November 01, 2019 | Street Rehabilitation | FWM + Thick Overlay (> 2.0 - 3.0)
Walden Road | South Major Drive | Willow Bend Drive | December 01, 2018 | March 01, 2019 | Concrete Pavement Repair
Wall Street | Jefferson Street | 200ft West of Archie Street | March 01, 2019 | June 01, 2020 | Street Rehabilitation | FWM + Thick Overlay (> 2.0 - 3.0)
WEBB LANE | VANS WAY | BRYANT WAY | March 01, 2022 | August 01, 2022 | Concrete Pavement Repair | PCC Jnt Rehab & Crk Seal
WELLINGTON PLACE | N DOWLEN ROAD | N DOWLEN ROAD | January 01, 2022 | June 01, 2022 | Street Rehabilitation | Edge Mill + Thin Overlay (1.5 - 2.0)
Wescalder Road | College Street | Humble Road | March 01, 2019 | August 01, 2020 | Street Rehabilitation | FWM + Thick Overlay (> 2.0 - 3.0)
Westgate Drive | Dowlen Road | Galway Drive | March 01, 2019 | June 01, 2020 | Street Rehabilitation | Edge Mill + Thin Overlay (1.5 - 2.0)
Westmont Drive | Diane Drive | 300 FT North of Diane Drive | December 01, 2018 | July 01, 2020 | Concrete Pavement Repair | PCC Localized Rehab
WESTPARK CIRCLE | MAJOR DRIVE | NORTH END | March 01, 2022 | September 01, 2022 | Concrete Pavement Repair | PCC Slight Pnl Rplcmnt (<10%) + Grind
Wiess Street | Magnolia Avenue | Grand Avenue | December 01, 2018 | April 01, 2021 | Concrete Pavement Repair | FWM + Thick Overlay (> 2.0 - 3.0)
WILLOW BEND DRIVE | S. MAJOR DRIVE | QUIET BEND | March 01, 2022 | September 01, 2022 | Concrete Pavement Repair | PCC Localized Rehab
Woodcrest Drive | Trinidad Road | South End | September 01, 2022 | March 01, 2023 | Pavement Preservation | FWM + Thick Overlay (> 2.0 - 3.0) + Strctrl Ptch
WOODLAWN AVENUE | CONCORD ROAD | WOODLAWN AVENUE | March 01, 2021 | March 01, 2021 | Street Rehabilitation | FWM + Thick Overlay (> 2.0 - 3.0)
WOODLAWN AVENUE | FRENCH ROAD | REDWOOD DRIVE | March 01, 2021 | March 01, 2021 | Street Rehabilitation | FWM + Thick Overlay (> 2.0 - 3.0)
Wren Way | Laurel Avenue | End of Cul-De-Sac | December 01, 2018 | February 01, 2020 | Concrete Pavement Repair | PCC Moderate Pnl Rplcmnt (< 20%) + Grind
Yount Street | Frost Street | Clinton Street | December 01, 2018 | November 01, 2019 | Concrete Pavement Repair | Routine Maintenance
4th Street |  |  | April 01, 2023 | September 01, 2024 | Street Rehabilitation | Surf Recon + Base Rehab / FWM + Strctrl Ptch + Olay
11th Street |  |  | September 01, 2019 | April 01, 2020 | Resurfacing | Surf Recon + Base Rehab / FWM + Strctrl Ptch + Olay
Griffing Road |  |  | June 01, 2020 | July 01, 2020 | Resurfacing | Surf Recon + Base Rehab / FWM + Strctrl Ptch + Olay
Old Dowlen Road |  |  | March 01, 2020 | April 01, 2020 | Resurfacing | EM/FWM + Moderate Overlay (2.0 - 3.0) + Strctrl Ptch
Old Voth Road |  |  | June 01, 2020 | August 01, 2020 | Resurfacing | EM/FWM + Moderate Overlay (2.0 - 3.0) + Strctrl Ptch
Pine Street |  |  | May 01, 2020 | August 01, 2020 | Resurfacing | EM/FWM + Moderate Overlay (2.0 - 3.0) + Strctrl Ptch
Piney Point Lane |  |  | June 01, 2020 | August 01, 2020 | Resurfacing | EM/FWM + Moderate Overlay (2.0 - 3.0) + Strctrl Ptch
Sherwood Drive |  |  | June 01, 2020 | August 01, 2020 | Resurfacing | Surf Recon + Base Rehab / FWM + Strctrl Ptch + Olay
Spindletop Avenue |  |  | March 01, 2022 | June 01, 2022 | Roadway and Drainage Rehabilitation | FWM + Thick Overlay (> 2.0 - 3.0) + Strctrl Ptch
Tram Road |  |  | October 01, 2020 | February 01, 2021 | Resurfacing | PCC Moderate Pnl Rplcmnt (< 20%) + Grind
Tram Road |  |  | October 01, 2020 | February 01, 2021 | Resurfacing | EM/FWM + Moderate Overlay (2.0 - 3.0) + Strctrl Ptch
Washington Boulevard |  |  | July 01, 2017 | November 01, 2021 | Street Rehabilitation | Surf Recon + Base Rehab / FWM + Strctrl Ptch + Olay