IJESRT

International Journal of Engineering Sciences & Research Technology

COMPARATIVE STUDY ON PLANNING, SCHEDULING & RESOURCE ALLOCATION OF A LIVE PROJECT WITH UPCOMING PROJECT OF SAME ASPECT.

Mohammed Nabeel Khan *, Prof. Akhil Khare, Himanshu Shrivastava

Oriental Institute of Science and technology, INDIA

DOI: 10.5281/zenodo.165008

ABSTRACT

The Aim of this study is to compare the actual project done with upcoming project in terms of planning, scheduling and resource allocating with respect to TIME & Cost. The actual project was subjected to a financial break up as a result, delay of project was observed. Now assuming that if financial break ups would not have occurred & allocation of resources would have done according to IS 7272 by taking CPWD rates 2014 then, best result was obtained w.r.t. time-cost for each activity in W.B.S. so for upcoming project which has same specification as actual project already done, new project duration, planning and resource allocation is performed & results are studied. Results are giving too main heading’s

- Amount saved on activity along with crashing & durations

- Amount invested on activity to achieve desired duration.

For this , total amount saved on project resource is compared to total amount invested to achieve target duration for upcoming project. Also, indirect cost which includes only the salary packages of PMC is also considered along with resource costing

.

KEYWORDS: planning, scheduling, resource allocation, PMC, MSP, durations.

INTRODUCTION

NOOR-US-SABAH Residencial project is working on cost plus contract type. This is a biggest project of central INDIA as per Standards. It is developed in 17.5 acres of land at a prime location of Bhopal. This Project is governed by Remigate infra developers pvt ltd.

Residential project are the project which have many factors for their successful completion. Most  important are the concept of pre-sales of unbuilt apartment which result like top gear in financial flow. This financial flow actions the rapid construction process, leading to good output in short duration. On the other hand, if sales result are poor this effect in delay of project leading to expansion of duration along with rises in prices of every construction activity.

Here the research work is on a broad view on this project is taken as a case study. Its full analysis and study is done on a basis of W.B.S. ( work breakdown structure), every activity of W.B.S. is quoted by D.P.R. ( daily progress report). Then on completion of two residential blocks, their resource cost and indirect cost is calculated along with the total duration invested on their completion.

This study is based on comparison of a live project with upcoming project to determine optimum project duration, planning and their respective resource allocation.

LITERATURE REVIEW

P.Dayakar and M. Udhayakumar (2012) described best schedule in such a way that meets the primary objectives of the total project. Those primary objectives are to create a quality project, completed on time, within budget, and in a safe work environment. Hence in this study an ongoing construction project is taken and the execution of the project is compared with the schedule with the help of Microsoft Project and concluded  that It is important to realize that there will be changes to the schedule logic as well as differences between the planned progress and actual progress.

METHODOLOGY

For preparing an overall comparative report, actual working data is collected by working at site and noting down daily progress report, with activity name, quantity of work done resources held. Then after completion of overall structural completion of construction of two blocks tables are prepared for upcoming project as follows:-]

RESULTS

RESULT ANALYSIS- TIME & COST COMPARISION

4.1         EXCAVATION

4.2.1 FOOTING WORK

4.3.1 RETAINING RAFT WORK

4.4.1. COLUMN WORK BASEMENT TO GROUND FLOOR

4.5.1 SLAB WORK

4.5.1 COLUMN GF TO FF

4.6.1 SLAB FIRST FLOOR

5.1.8 COLUMN WORK FROM 1ST FLOOR TO 2ND FLOOR

5.1.9. 2ND FLOOR SLAB WORK

5.1.10 COLUMN CASTING FROM 2ND TO 3RD  FLOOR.

5.1.11 SLAB CASTING 3RD FLOOR.

5.1.12 COLUMN CASTING FROM 3RD TO 4TH FLOOR.

5.1.14 SLAB CASTING 4TH FLOOR.

5.1.15 COLUMN CASTING 4TH TO 5TH FLOOR

5.1.16 5TH FLOOR

5.1.17 COLUMN CASTING FROM 5TH TO TERRACE FLOOR

5.1.18 TERRACE SLAB

5.1.18 MUMTY COLUMN

5.1.19 MUMTY SLAB

5.2.1 INDIRECT COST COMPARISON

5.3.1 OVERALL LABOUR RESOURCE COST

5.3.1. OVERALL COST

CONCLUSION

AS PER RESULTS IT CAN BE CONCLUDED THAT BY DECREASING THE DURATION OF A PROJECT BY PROPPER SCHEDULING AND STARTING ACTIVITIES SIMULTANEOUSLY, DURATION IS DECREASE AND CHANCES OF DELAYING THE PROJECT IS MINIMISED WHEREAS COST OF RESOURCES, OVERALL PROJECT  IS INCREASING BUT INDIRECT COST WILL DECREASE. THE ABOVE  RESULTS CAN ONLY BE OBTAINNED UNDER NO FINANCIAL BREAKUP CONDITION.

HERE WE USE MICROSOFT PROJECT FOR PROPER SCHEDULING AND RESOURCE ALLOCATION.

Project Duration for Upcoming Project is found by Critical Path analysis from CPM Network charts.

FUTURE SCOPE

- This comparative study can help the working p.m.c to get pre remedies for any activity which was delayed at greater extent at actual project done. and thus preventing any breakup in working schedule.

- Here we have taken residencial buuilding project in future study can be done on highway project.

- In this study microsoft project has been taken in future primavvera siftware can be used instead of msp.

##### REFERENCES

- Planning & scheduling by using Microsoft project: a case study of “suggestion for construction and completion the science department for university islam antarabangsa Malaysia, Bandar indera mahkota,kuatan, Pahang” by Mohd Johari Bin Othman

- A Project Management approach using Erp and Primavera in construction industries by Miss A A. LAKADE, Prof. A K.Gupta, Prof. D B. Desai

- Project Planning Techniques for Academic Advising and Learning by Vittal Anantatmula Projects and Their Management by Guru Prakash Prabhakar

- MS PROJECT for construction schedulers (2011) by Ron Winter, PSP, F. Burak Evrenosoglu Analyzing project management research: Perspectives from top management journals by Young Hoon, Kwak, Frank T. Anbari

- Optimal planning and scheduling in multi-storied building by R.Prabhahar,G.ravichandran Project management software and its utilities (2014) by Hoang, Nhat Minh Shrestha, Swostik Central Public Works Department Analysis of Rates –Delhi

- MAHARASHTRA JEEVAN PRADHIKARAN schedule of rates for the year 2012-13

- Project Management Body of Knowledge (2000) edition.