## Introduction
To create this planning model, we analysed legislation across a range of key countries, relevant accessibility standards and examined existing advice. We consulted with publishers to enable us to tailor guidance specifically to the sector of small diamond open access presses.
We grouped the steps into 4 sections: preparation, analysis and auditing, implementation, and improvements and benchmarking.
For each step, we have given a short overview description of what it involves.
We also created a comprehensive guide to the steps available in Copim Compass (live link to follow), which links out to various resources, such as legislation guides, standard specifications and the most widely used existing guidance in each area.
For each step, we also suggest publishers might want to plan and consider the following: whether the editor/publisher, author typesetter or a third party will be completing the work, where and how within current workflows the work will be completed, how long you expect each step to take and what deadlines you will set for yourself.
Please give feedback on the notes above, and any aspect of the planning model, thankyou!

## Planning Model
A Preparation |  | Description
1 | Accountability | Appoint a person to co-ordinate accessibility, who could be a dedicated accessibility professional or someone who has a wider portfolio of work that includes accessibility too. However, it's also important to remember that some accessibility work will be completed by almost everyone at an organisation.
2 | Training | Plan technical digital accessibility training and support the identified staff to develop skills.
3 | Identify Objectives | Once relevant staff have been identified and trained, some organisational accessibility objectives can be devised through requirements gathering exercises. Any organisation should aim to meet legal minimum requirements, but it's possible to be exempt from that (this requires work to evidence), and you may decide to go beyond in some areas if it fits with your organisational values. Also, your readership might already have made accessibility requests you haven't been able to meet yet, or you could survey your end users to capture this 'reader voice' in terms of accessibility requirements. Finally, it's possible there are some community or discipline specific considerations to include as well.
B Analysis and Auditing
4 | Baseline Auditing | Audit the current accessibility of all aspects of the organisation, including the frontlist and backlist book files, the website functionality and the backend submission platform. You could complete this yourself using self auditing, or employ an external auditor. You could also look at assessing current organisational knowledge, attitudes towards and motivations for engaging with accessibility work.
5 | Available and Required Capacity and Budget | Improving accessibility requires dedicated time and money, and a full consideration of where this can be diverted to accessibility goals will help with planning. It is likely that you will have some idea of how long book production tasks take, and how much extra work accessibility improvements will add to that, but it could be that you will need to understand more about the relative simplicity or complexity of individual accessibility requirements (like ALT text, or checking colour contrast).
C Implementation
6 | Documentation | Capturing the results of identifying objectives, auditing, and analysing resources might happen across a range of documentation that could include: an accessibility policy, roadmaps, strategic plans, updated author guidelines, or other documentation.
7 | Plan Work | We recommend that frontlist and backlist/remediation are considered separately, and separate plans for the website including the backend submission process.
8 | Public Statements | Publish accessibility statements and roadmaps on the organisation's website, and include VPATs and public policies if that is decided on.
D Improvements and Benchmarking
9 | Improvements | Incorporate planned accessibility improvements into workflows and complete the plan.
10 | Benchmark Auditing | Audit the accessibility and organisational knowledge at regular intervals within the plan to showcase improvements.

## BLANK Self Assessment Tool
Section | Step | Title | Tasks | Recommended or Optional | 0 - Unaware | 1 - Aware but not actioned | 2 - Trying to action but some barriers | 3 - Starting to action | 4 - In the middle of actioning | 5 - Actioned and achieved | n/a | Current Level | Desired Level | Achieved Level (after some improvements made)
A Preparation | 1a | Accountability | Appoint a person to co-ordinate accessibility | Recommended
A Preparation | 1b | Accountability | Ensure the whole press is aware they need to engage with accessibility tasks | Recommended
A Preparation | 1c | Accountability | Consider external certification services | Optional
A Preparation | 2a | Training | Identify sources of suitable accessibility training | Recommended
A Preparation | 2b | Training | Consider custom paid for accessibility training | Optional
A Preparation | 2c | Training | Support the identified accessibility co-ordinator to develop skills | Recommended
A Preparation | 3a | Identify Objectives | Consider applicability of legislation and whether the press is exempt (if so, plan to evidence this) | Recommended
A Preparation | 3b | Identify Objectives | Complete requirements gathering from readership | Optional
A Preparation | 3c | Identify Objectives | Capture community / discipline specific considerations | Optional
B Analysis and Auditing | 3d | Identify Objectives | Consider where you might decide to go beyond legal minimum (parts of WCAG AAA or other accessibility features requested by readership or research discipline) | Optional
B Analysis and Auditing | 4a | Baseline Auditing | Consider capturing current organisational knowledge, attitudes towards and motivations for engaging with accessibility work | Optional
B Analysis and Auditing | 4b | Baseline Auditing | Complete Automated Testing | Recommended
B Analysis and Auditing | 4c | Baseline Auditing | Complete Manual Testing | Recommended
B Analysis and Auditing | 4d | Baseline Auditing | Complete Assistive Technology Tests | Optional
B Analysis and Auditing | 4e | Baseline Auditing | Complete End User Testing from Print Disabled People | Optional
B Analysis and Auditing | 4f | Baseline Auditing | Consider external auditing services | Optional
C Implementation | 5a | Available and Required Capacity and Budget | Frontlist: Use checklist with complexity and current knowledge of workflows to estimate time required to complete accessibility tasks | Recommended
C Implementation | 5b | Available and Required Capacity and Budget | Backlist: Use checklist with complexity and current knowledge of workflows to estimate time required to complete accessibility tasks | Recommended
C Implementation | 5c | Available and Required Capacity and Budget | Plan and assign budget | Recommended
C Implementation | 6a | Documentation | Plan documentation that could include: an accessibility policy, roadmaps, strategic plans, updated author guidelines, or other documentation | Recommended
C Implementation | 6b | Documentation | Create an Accessibility Policy | Optional
C Implementation | 6c | Documentation | Update Author Guidelines to include accessibility tasks | Recommended
C Implementation | 7a | Plan Work | Front list / Born Accessible - Create accessible book files | Recommended
C Implementation | 7b | Plan Work | Back list / Remediation - Upgrade the accessibility of existing book files | Recommended
C Implementation | 7c | Plan Work | The Website functionality - Improve accessibility of HTML books and whole website | Recommended
C Implementation | 8a | Statements | Create an Accessibility Statement on a public web page | Recommended
C Implementation | 8b | Statements | Update your initial VPAT | Optional
C Implementation | 8c | Statements | Consider sharing the Accessibility Policy openly, if decided on | Optional
D Improvements and Benchmarking | 9 | Improvements | Complete the plan | Recommended
D Improvements and Benchmarking | 10 | Benchmark Auditing | Audit again at regular intervals | Recommended

## EXAMPLE Self Assessment Tool
Section | Step | Title | Tasks | Recommended or Optional | 0 - Unaware | 1 - Aware but not actioned | 2 - Trying to action but some barriers | 3 - Starting to action | 4 - In the middle of actioning | 5 - Actioned and achieved | n/a | Current Level | Desired Level | Achieved Level (after some improvements made)
A Preparation | 1a | Accountability | Appoint a person to co-ordinate accessibility | Recommended | [5 empty] | Joanne Fitzpatrick agreed to be accessibility co-ordinator |  | 5 | 5
A Preparation | 1b | Accountability | Ensure the whole press is aware they need to engage with accessibility tasks | Recommended |  |  |  | Upcoming meeting planned to discuss changes we need to make |  |  |  | 3 | 5
A Preparation | 1c | Accountability | Consider external certification services | Optional |  |  |  |  | Currently looking at the suggested certification services on Compass but implications not fully understood yet |  |  | 4 | 5
A Preparation | 2a | Training | Identify sources of suitable accessibility training | Recommended |  |  |  | Looking at list of free training on Compass |  |  |  | 3 | 5
A Preparation | 2b | Training | Consider custom paid for accessibility training | Optional | [5 empty] | Definitely do not have budget for bespoke training |  | 5 | 5
A Preparation | 2c | Training | Support the identified accessibility co-ordinator to develop skills | Recommended |  |  | Incredibly difficult to find time capacity to achieve this |  |  |  |  | 2 | 4
A Preparation | 3a | Identify Objectives | Consider applicability of legislation and whether the press is exempt (if so, plan to evidence this) | Recommended |  |  | Very difficult to understand, not sure if we are exempt or not |  |  |  |  | 2 | 5
A Preparation | 3b | Identify Objectives | Complete requirements gathering from readership | Optional | [6 empty] | Not going to do this one | n/a
A Preparation | 3c | Identify Objectives | Capture community / discipline specific considerations | Optional | [6 empty] | Not going to do this one | n/a
B Analysis and Auditing | 3d | Identify Objectives | Consider where you might decide to go beyond legal minimum (parts of WCAG AAA or other accessibility features requested by readership or research discipline) | Optional | [6 empty] | Not going to do this one | n/a
B Analysis and Auditing | 4a | Baseline Auditing | Consider capturing current organisational knowledge, attitudes towards and motivations for engaging with accessibility work | Optional | [6 empty] | Not going to do this one | n/a
B Analysis and Auditing | 4b | Baseline Auditing | Complete Automated Testing | Recommended |  | Aware we will need to do this but no work completed yet | [5 empty] | 1 | 4
B Analysis and Auditing | 4c | Baseline Auditing | Complete Manual Testing | Recommended |  | Aware we will need to do this but no work completed yet | [5 empty] | 1 | 4
B Analysis and Auditing | 4d | Baseline Auditing | Complete Assistive Technology Tests | Optional |  | Would like to do this | [5 empty] | 1 | 3
B Analysis and Auditing | 4e | Baseline Auditing | Complete End User Testing from Print Disabled People | Optional |  | Would like to do this | [5 empty] | 1 | 3
B Analysis and Auditing | 4f | Baseline Auditing | Consider external auditing services | Optional | [5 empty] | Definitely do not have budget for external auditing |  | 5 | 5
C Implementation | 5a | Available and Required Capacity and Budget | Frontlist: Use checklist with complexity and current knowledge of workflows to estimate time required to complete accessibility tasks | Recommended |  |  |  | Currently looking at this |  |  |  | 3 | 4
C Implementation | 5b | Available and Required Capacity and Budget | Backlist: Use checklist with complexity and current knowledge of workflows to estimate time required to complete accessibility tasks. | Recommended |  |  |  | Currently looking at this |  |  |  | 3 | 4
C Implementation | 5c | Available and Required Capacity and Budget | Plan and assign budget | Recommended |  |  |  | Currently looking at this |  |  |  | 3 | 5
C Implementation | 6a | Documentation | Plan documentation that could include: an accessibility policy, roadmaps, strategic plans, updated author guidelines, or other documentation. | Recommended |  |  |  | Currently looking at this |  |  |  | 3 | 4
C Implementation | 6b | Documentation | Create an Accessibility Policy | Optional | [6 empty] | Not going to do this one | n/a
C Implementation | 6c | Documentation | Update Author Guidelines to include accessibility tasks | Recommended |  |  |  | Currently looking at this |  |  |  | 3 | 5
C Implementation | 7a | Plan Work | Front list / Born Accessible - Create accessible book files | Recommended |  | Not started yet, still planning | [5 empty] | 1 | 3
C Implementation | 7b | Plan Work | Back list / Remediation - Upgrade accessible book files | Recommended |  | Not started yet, still planning | [5 empty] | 1 | 3
C Implementation | 7c | Plan Work | The Website functionality - Improve accessibility of HTML books and whole website | Recommended | Have only thought about book files so far | [6 empty] | 0 | 3
C Implementation | 8a | Public Statements | Create an Accessibility Statement on a public web page | Recommended |  | Didn't know about this so not looked at it yet | [5 empty] | 1 | 5
C Implementation | 8b | Public Statements | Update your initial VPAT | Optional | Not sure what this is, more scoping work needed | [6 empty] | 0 | 1, maybe n/a
C Implementation | 8c | Public Statements | Consider sharing the Accessibility Policy openly, if decided on | Optional | [6 empty] | Not going to do this one | n/a
D Improvements and Benchmarking | 9 | Improvements | Complete the plan | Recommended |  | Still at beginning stages as yet | [5 empty] | 1 | 4
D Improvements and Benchmarking | 10 | Benchmark Auditing | Audit again at regular intervals | Recommended |  | Still at beginning stages as yet | [5 empty] | 1 | 4