Policy Memo

LMU Munich

Geschwister-Scholl-Institute of Political Science

Seminar: 15039 What Happened with EU Money? Member States in the Final Year of the COVID-19 Recovery and Resilience Facility

Instructor: Dr. Tiziano Zgaga

Policy Memo

Analysis of Slovakia’s Request for the Next Tranche

of the Recovery and Resilience Plan

Author: Oliver Suchý

Matriculation Number: 13161791

Email: oliver.Suchy@campus.lmu.de/ 
Personal Email: suchyoliver2001@gmail.com

Characters Count: 28 838

Declaration of originality

I hereby declare that I have written this seminar paper on my own, have not used any sources or aids other than those specified, and have marked the passages taken from them as such. All aids used are listed in the table below. Regarding the use of Large Language Models (LLM, e.g., Chat-GPT), I have archived the entire LLM interaction history with reference to the submitted work and can present it upon request. This seminar paper has not been presented in this or a similar form in any other course.

| Name of aid | Purpose |
| --- | --- |
| ChatGPT | In section 3 (Plan Implementation and Absorption Policy) AI have been used to translate the NRRP from Slovak to English, since the author speaks Slovak, he worked in the Slovak language, which he later translated using AI and pasted into the term paper. |
|  | https://chatgpt.com/share/69762783-183c-800f-af1e-369276010149 |

Executive Summary

The COVID-19 pandemic caused significant economic consequences in Slovakia and revealed structural weaknesses, particularly the country's high dependence on the automotive industry and exports. Although the main macroeconomic indicators stabilized by the end of 2022, negative effects persist in the areas of education, tourism, and human capital formation. The National Recovery and Resilience Plan (NRRP), with a total budget of EUR 6.4 billion, financed exclusively through grants, is the main instrument for supporting economic recovery and implementing the green and digital transformation. The implementation of the NRRP is ensured by a centralized management structure led by the National Implementation and Coordination Agency (NIKA), supplemented by a control, audit, and monitoring system and a zero-tolerance policy towards fraud and corruption. After three approved revisions, the plan continues to meet all EU requirements and maintains the original overall allocation. The cross-border effects of other Member States' plans are expected to further strengthen the economic impact of the NRRP, with Slovakia among the largest beneficiaries of the spill-over relative to GDP.

On November 25, 2025, Slovakia submitted its seventh payment request for EUR 761.2 million, which includes 18 milestones in the areas of education, healthcare, justice, digitization, the fight against corruption, and REPowerEU measures. Fifteen milestones have been met. Two milestones are on track and expected to be completed, and one milestone relating to the modernization of IT equipment in courts (C15/I2) is delayed and is currently not sufficiently documented publicly.

Given the Slovak Republic's high rate of compliance with its commitments to date and its reliable implementation history, it is recommended that the seventh payment request be approved, subject to clear and evidence-based fulfillment of the remaining milestone. Before the funds are released, the Ministry of Justice should formally adopt the relevant investment measures and provide verifiable evidence of their implementation in accordance with the requirements of the Recovery and Resilience Facility.

Table of Contents

1. Pandemic Impact on Slovakia	5

2. Slovakia’s Recovery and Resilience Plan (NRRP)	6

3. Plan Implementation and Absorption Capacity	7

3.1. Implementation Architecture	8

3.2. Coordination and anti-Freud Policy	8

3.3. Economic Impacts of the RRF in Slovakia	9

4. The Next Trench of the NRRP	9

4. Final Assessment of the Next Trench	10

References	12

Annex	15

Graphs	16

Tables	20

Figures	22

## 1. Pandemic Impact on Slovakia

During and after the COVID-19 pandemic Slovak Republic experienced a historical economic decline affecting all levels of society – national and private, and gradually negatively affected the quality of life (Petrovič & Maturkanič, 2022; Tomková et al., 2023). Impacts on the economy have been deepened, as in 2019, before the pandemic, in Q2, the gross domestic product increased by 3.7% to the year before, but later, when the pandemic broke out 
the Slovak GDP decreased by 8.9% in the Q2 in 2020 due to the decrease of exports, lowering of foreign demand and domestic measures to increase the safety of citizens. The economy’s lack of diversification has been pinpointed by the policy-makers, and became apparent during the COVID-19. Automobile production, including smaller local suppliers, made up nearly half of industrial output and 47% of total exports. All four of the country’s car manufacturers completely stopped production in April 2020, but partially resumed operations in May (European Bank for Reconstruction and Development, 2020). Indeed, in Q2 in 2021, the GDP increased by volume of 12.7%; however, in relation to the previous year, meaning 
that the economy started to stabilise itself until Q4 in 2022, when the economic growth slowly reached the numbers just before the pandemic (Statistical Office of the Slovak Republic, 2025a). Moreover, the general macroeconomic performance decreased rapidly after the start 
of the crisis (Ibrahim & Ozturk Ofluoglu, 2025).

Generally, the main macroeconomic indicators proved the impact of the COVID-19 pandemic to Slovak economy and production. The positive trends before the crisis changed drastically, and the Slovak economy was stagnating and healing for the next few years. Namely, 
in the indicators of GDP growth, government balance, net flow of investment, external debt, general government gross debt and unemployment rate (European Bank for Reconstruction 
and Development, 2022)

The negative implications of the crisis, together with Russian aggression directly on Slovakia’s border, are catalyzed with a decrease of 54% accommodated tourists (Petrikovičová et al., 2023) and a drop in the nominal input of roughly 50% (Statistical Office of the Slovak Republic, 2025b). Moreover, the COVID-19 crisis negatively affected education. In addition 
to its immediate impact on education and social development, school closures are expected 
to have long-lasting effects on children’s economic outcomes and earnings. The World Bank (2020) estimates that a loss of 0.6 years of schooling could reduce the future monthly earnings of students by €872. According to data from the Organisation for Economic Co-operation and Development (Hanushek & Woessmann, 2020), each additional year of school increases wages by 7.5–10%. This means that a loss of one-third of a school year would result in a reduction 
of approximately 3 percentage points. For Slovakia, the closure of schools during the first wave was estimated to reduce the lifetime earnings of primary and secondary school students 
by 0.3–0.9% (Hellebrandt, 2020).

## 2. Slovakia’s Recovery and Resilience Plan (NRRP)

COVID-19 impacts were drastic throughout the world. The European Commission adopted NextGenerationEU, which is an instrument designed to address the immediate economic 
and social impacts of the COVID-19 crisis. With its core component Recovery and Resilience Facility (RRF), the EU aims to ensure an effective and more rapid recovery of the Member States (European Commission, n.d.-a). The Member States create their NRRP to address 
the specific structural and macroeconomic challenges identified in the European Semester, while aligning fully with NextGenerationEU priorities on digitalisation and the green transition (European Commission, n.d.-b).

Slovakia has so far received €3.96 billion out of the total €6.408 billion allocated 
under the Facility, corresponding to 5.21% of its GDP. The entire €6.408 billion grant has been provided in the form of grants, without any loans allocated (European Commission, n.d.-c).

## 3. Plan Implementation and Absorption Capacity

The Recovery and Resilience Plan was adopted in 2021 and underwent a first revision 
in 2022–2023, which primarily reflected the inclusion of the new green REPowerEU plan aimed at reducing dependence on Russian fossil fuels and decreasing the effects of the climate crisis, the recalculation of 30% of the allocation based on GDP growth in 2020–2021 
on the principle of solidarity (which, due to the faster recovery of the economy, reduced Slovakia’s allocation by 323 million EUR), and the impact of high inflation on energy 
and construction material prices, leading to higher unit costs and a reduction of some targets. The revision had to comply with strict criteria: maintaining at least 20% of expenditure 
on digital and 37% on green measures, respecting the Council’s recommendations, avoiding significant harm to the environment, not fundamentally changing reforms, and not shifting 
a substantial share of targets to the end of the implementation period, while new measures could only be added within the REPowerEU chapter. Slovakia submitted the revised plan 
on 26 April 2023, the European Commission gave it a positive assessment on 27 June 2023, and the ECOFIN Council approved it on 14 July 2023. The second revision, submitted 
on 21 March 2025, pursuant to Article 21 of Regulation (EU) 2021/241, adjusted measures 
that could not be fully implemented, strengthened those with sufficient absorption capacity (so-called scale-up measures) and added new measures; it was approved by ECOFIN 
on 13 May 2025. The third revision of 2 October 2025, initiated by the European Commission with the aim of simplifying implementation and maximising the likelihood of achieving 
the milestones and targets, was approved by the ECOFIN Council on 13 November 2025, 
with the total allocation of the Recovery and Resilience Plan for the Slovak Republic amounting to EUR 6.4 billion remaining unchanged even after the second and third revisions (Plán obnovy, n.d.-a).

### 3.1. Implementation Architecture

The EU Recovery and Resilience Facility was created after the outbreak of the COVID-19 pandemic as an instrument to finance strategic reforms and investments, aimed at mitigating the economic and social impacts of the crisis and supporting the green and digital transformation. At the Government Office of the Slovak Republic, NIKA (National Implementation and Coordination Agency) was established as the national contact point 
and central coordinator of the Recovery and Resilience Plan for the period 2021–2026. 
The national project (2021-2023) focuses on building human and institutional capacities 
for the management, coordination, control, and audit of the Plan, including the preparation 
of legislation, methodologies, the implementation system, and updates of the Plan. The Ministry of Finance of the Slovak Republic and the Office of Government Audit are also involved in the management and control system. The activities include training, workshops 
and conferences for entities involved in implementation. For each payment request, a summary of the audits carried out is submitted to the European Commission, including findings 
and corrective measures, with a focus on preventing and detecting fraud, corruption 
and conflicts of interest (Ministry of Finance of the Slovak Republic, n.d.).

### 3.2. Coordination and anti-Freud Policy

NRRP in the Slovak Republic is governed by Intergovernmental Committees consisting 
of members from every ministry, except the Ministry of Defence, Public Procurement Office, Government Office of the Slovak Republic, and Research and Innovation Authority, mandated by the government of the state (Plán Obnovy, n.d.-b).

The Recovery Plan Section of the Office of the Deputy Prime Minister for the Recovery Plan and the Knowledge Economy of the Slovak Republic, which serves as the National Implementation and Coordination Authority (NIKA), follows a strict zero-tolerance policy 
on fraud and corruption. It is committed to working in a transparent, honest, and impartial way and to respecting high legal and ethical standards. The goal of its anti-fraud and anti-corruption policy is to strengthen transparency, prevent risks early, quickly detect suspicious behaviour, and make sure that all cases are properly investigated and fairly punished (Office of the Deputy Prime Minister of the Slovak Republic for the Recovery Plan and the Knowledge Economy, n.d.).

### 3.3. Economic Impacts of the RRF in Slovakia

According to the report by the European Commission (2025), with the effect of spillovers from other Member States’ RRPs, the allocation is expected to increase the amount allocated by 10% from the initial request of EUR 6.4 billion to 7.02 billion. Slovakia is the highest beneficiary from spillovers relative to GDP, with a 1.8% increase, due to high integration within the European Single Market. Spillover impacts arise from higher exports to other Member States due to the implementation of the NRRP. Slovakia’s NRRP consists in total 
of 63 reforms, of which almost half are aimed towards the labour market (16) and green transition (15). These reforms consist, for example, of A reform to improve the long-term fiscal sustainability of the pension system or A national strategy for Research, Development and Innovation (RDI) (European Commission, 2025).

## 4. The Next Trench of the NRRP

On the 25th of November 2025, Slovakia submitted the 7th payment request of EUR 761.2 million (European Commission, n.d.-e; Plán obnovy, 2025). Part of the requests are 18 milestones focusing on healthcare, education, digitalization, and environment. National Implementation and Coordination Agency (NIKA) urges that non-fulfillment of one milestone can lead 
to the block of the whole payment. For that reason, NIKA is regularly evaluating the milestones and their fulfilment. NIKA concluded, on the 5th of December 2025, that in the 7th request, two milestones are going according to the plan, yet are not fulfilled. The first one 
is milestone 1, ‘Increasing the capacity of the Slovak Environmental Inspectorate’, 
from C4 – decarbonisation from the Ministry of Environment. The second one is milestone 14, ‘Extent of renovated floor area of police buildings with a view to reducing the energy intensity of the buildings (in m²)’, from C16 - Fight against corruption and money laundering, 
from the Ministry of Interior. Out of 18 milestones, there is, however, one which is delayed, yet expected to be completed before the submission, namely, it is milestone 17, ‘Modernisation of court IT equipment for court staff’, from C15 – Reform of Justice. All in all, 15 milestones have been successfully completed. Out of all 18 milestones, two milestones 
are C6 - Availability, development and quality of inclusive education; two milestones 
are C11 - Modern and accessible healthcare; two milestones are C12 - Humane, modern 
and accessible mental health care; two milestones are C13 - Accessible and high-quality long-term social and healthcare services; one milestone is C14 - Improvement of the business environment; one milestone is C15 - Justice reform; two milestones are C16 - Fight against corruption and money laundering; one milestone is C17 - Digital Slovakia; and four milestones are RePowerEU (Plán obnovy, n.d.-c).

Due to COVID-19 and health protection regulations in 2020, the Slovak schools have been partially or fully closed for a long period of time (Petrikovičová et al., 2023). The 7th payment includes measures to counter. According to the Ministry of Education (n.d.), the C6 consists 
of 6 reforms and 1 investment, which, for example, will ensure that every child under 5 years of age will have a place in pre-educational institutions; improvement of the mental health 
of students and children; desegregation measures; or decarbonization of the buildings.

## 4. Final Assessment of the Next Trench

This policy memo summarises the pandemic’s impacts on Slovakia, with a particular focus 
in the education sector. It then outlines Slovakia’s implementation approach 
under the National Recovery and Resilience Plan (NRRP), including absorption measures 
and the country’s anti-fraud and anti-corruption capacity.

As of the 7th payment request submitted on 25 November 2025, the European Commission 
had positively assessed the relevant milestones and disbursed nearly EUR 3.9 billion 
to Slovakia. In addition, in January 2026, the Commission accepted Slovakia’s 6th payment (European Commission, n.d.-c).

The 7th payment request covers 18 milestones. One milestone - C15, Investment 2 (“Support tools for the judicial map reform - digitisation of tools, modernisation of IT equipment, 
and analytical capacities”) - is delayed, and should therefore be assessed as a specific implementation risk for the overall payment decision, notwithstanding the memorandum’s primary focus on education impacts. While completion has been reportedly expected before the Commission’s final assessment of the 7th payment request, neither the Ministry of Justice nor the NIKA currently provides clear public information on the milestone’s targets, implementation status, or evidence of completion (Plán Obnovy, n.d.-c).

Given Slovakia’s strong record of timely and accurate delivery across the previous six payment requests, acceptance of the 7th payment request is recommended, only subject to a clear, evidence-based condition. Prior to disbursement, the Ministry of Justice should (i) formally adopt the investment measures, and (ii) provide verifiable proof of implementation consistent with the milestone. The decision pathway should be explicit - either withholding disbursement until C15/I2 is completed, or sufficiently proven, or proceeding with the request while conditioning the release of funds on documented completion of the milestone.

## References

European Bank for Reconstruction and Development, (2020). Slovak Republic. In Transition report 2020-21: The state strikes back. European Bank for Reconstruction and Development.

European Bank for Reconstruction and Development, (2022). The Slovak Republic diagnostic 2022. https://www.ebrd.com › country-strategies › slovak

European Commission, (n.d.-a). Recovery plan for Europe. European Union. https://commission.europa.eu/strategy-and-policy/recovery-plan-europe_en

European Commission, (n.d.-b). Recovery and Resilience Facility. European Union. https://commission.europa.eu/business-economy-euro/economic-recovery/recovery-and-resilience-facility_en

European Commission. (n.d.-c). Recovery and Resilience Scoreboard: Country overview – Slovakia. European Union. Retrieved January 23, 2026, from https://ec.europa.eu/economy_finance/recovery-and-resilience-scoreboard/country_overview.html?country=Slovakia

European Commission. (n.d.-e). Recovery and Resilience Scoreboard: Timeline – Slovakia. Retrieved January 23, 2026, from https://ec.europa.eu/economy_finance/recovery-and-resilience-scoreboard/timeline.html?country=Slovakia

European Commission. (2025, July). The impact of the Recovery and Resilience Facility in Slovakia [PDF]. https://commission.europa.eu/document/download/3cca8ae1-d5ab-4c97-89b0-050fde3bb18d_en?filename=250611%20RRF_impact_SK_v4_PRINT.pdf

Hanushek, E. A., & Woessmann, L. (2020). The economic impacts of learning losses (OECD Education Working Papers, No. 225). OECD Publishing. https://doi.org/10.1787/21908d74-en

Hellebrandt, T. (2020). Koľko stratia deti na budúcich príjmoch kvôli zatvoreným školám? [How much will children lose in future income due to closed schools?]. Ministry of Finance of the Slovak Republic. https://www.mfsr.sk/sk/financie/hodnota-za-peniaze/blogy-uhp/2020/vplyv-zatvorenych-skol-buduce-prijmy-ziakov/?forceBrowserDetector=blind

Ibrahim, A., Ozturk Ofluoglu, N. (2025). Measuring Slovakia’s macroeconomic performance with Kaldor’s magic square. Economic Review, 54(4), 235 ─ 255. https://doi.org/10.53465/ER.2644-7185.2025.4.235-255

Ministry of Education, Science, Research and Sport of the Slovak Republic. (n.d.). Component 6: Accessibility, development and quality of inclusive education at all levels. Retrieved January 27, 2026, from https://www.minedu.sk/komponent-6-dostupnost-rozvoj-a-kvalita-inkluzivneho-vzdelavania-na-vsetkych-stupnoch/

Ministry of Finance of the Slovak Republic. (n.d.). Building the implementation structure for the implementation of the Recovery and Resilience Facility. Retrieved January 24, 2026, from https://www.mfsr.sk/sk/projekty-mfsr/projekty-mfsr/projekty-op-evs/budovanie-implementacnej-struktury-implementaciu-mechanizmu-podporu-obnovy-odolnosti.html?forceBrowserDetector=blind

Office of the Deputy Prime Minister of the Slovak Republic for the Recovery Plan and the Knowledge Economy. (n.d.). Anti-fraud policy. Retrieved January 24, 2026, from https://www.planobnovy.sk/site/assets/files/2958/politka-boja-proti-podvodom.pdf

Petrikovičová, L., Petrikovič, J., Kurilenko, V., Taraj, M., Kholov, S., & Azizi, M. (2023). Impact of the Global COVID-19 Pandemic on the Slovak Economy (Tourism and Education). Journal of Education Culture and Society, 14(2), 468-483.

Petrovič, F., & Maturkanič, P. (2022). Urban-Rural Dichotomy of Quality of Life. Sustainability, 14(14), 8658, https://doi.org/10.3390/su14148658

Plán obnovy, (n.d.-a). Kompletný plán obnovy. Retrieved January 24, 2026, from https://www.planobnovy.sk/kompletny-plan-obnovy/

Plán obnovy. (n.d.-b). Otázky a odpovede. Retrieved January 24, 2026, from https://www.planobnovy.sk/otazky-a-odpovede/

Plán obnovy. (n.d.-c). 7. žiadosť o platbu [7th payment request]. Retrieved January 24, 2026, from https://www.planobnovy.sk/realizacia/semafor/7-ziadost-o-platbu/

Plán obnovy. (2025, November 28). Slovakia has requested the disbursement of €761 million from the Recovery Plan [Slovensko požiadalo o vyplatenie 761 mil. eur z plánu obnovy]. Retrieved January 24, 2026, from https://www.planobnovy.sk/aktuality/slovensko-poziadalo-o-vyplatenie-761-mil-eur-z-planu-obnovy/

Statistical Office of the Slovak Republic, (2025a). Gross domestic product in the 2nd quarter of 2025. https://slovak.statistics.sk/wps/portal/ext/products/informationmessages/inf_sprava_detail/1578d489-3b04-4c23-910f-fab7d44c2a2a/!ut/p/z1/tVJNb6MwFPwte-Bo_MCmdnpzojYfm1TbpGkSX1aGmEATMAUvNP31NVUvlbYfe1hf7CfNjGbeGEu8xbJUbX5QNjelOrl5Jy9-37IpHw4DATCcE5jOfq5uJqPrcLyO8OY9gN8sr2B6J36NlzMaAI2w_Jx_jyWWSWkrm-GdiRuVoeaI8jJF6mg9cA9TF85NW2rUVLVqzx60jbZHdwcR43vKB4jEQBFNQoIGAaQoVTHbUzerUPXyVZLv8e5b6M1Xefs48MER4PjyFTIaiwllcwA-H0cwFZP1cnBLCAjyBvhEY-c8sA89BAxv2lx3eF32mznh1T9GnACefdWKqz2sF6PFwSkrm_V9GLz9lryj5g-Pj1K4Wk1p9ZPF2__Rq8uQx4XfJYUPPuMMCGOchnRwERHSuxBlTLgLUOtU17r2_9TuO2fWVs2lBx50XecfjDmctJ-YwoO_UTLTOPfvkbgq1gUnZ3RMF1eEyvhMnud6I368AIJvrdw!/dz/d5/L2dBISEvZ0FBIS9nQSEh/

Statistical Office of the Slovak Republic, (2025b). Tourism Satellite Account 2023. https://slovak.statistics.sk/wps/portal/ext/products/informationmessages/inf_sprava_detail/!ut/p/z0/zVVNU-JAEP0rXjg26fmeOaJVsrpqFWupyGVrvgLZQIIksIu_fgesdaVKEPe0l2TSybx-r_O6Jxtlw2xU2VUxtm1RV3aanh9H8vtAXejTU9JDPL1ieHH59fbmy9k57d-J7DZW2WU2Ktys-9PPutjVkhhUlBpCkQsiNhDFj6enUS8b-bpq4682G9ausRNoyg5aVy_bWWwaO45NB4mA3JbtcrEGioSlAHM0ZzKARSuB51qBDcZDzhjxHmnkOt-koIvrs-txNprbdgJFldfZ8KitO9yN0EYh0YYZwxg1e4C95cQFLcHbPABHEUBHQYHKIMw2q1Ofk426e1IHILrLu0m3hPkiTqY2wLMt7XMRS2igKp7LegmTOlR1Wy87eBSNHX2caY0MCUdKTJL4AcmmTTbwsH1TtR2cL-qwLNt1Wi3dtCitL2IHS9vaaT0-eY0Ve8r2zoc77AjVSnJKuDaUpfUBdrGChLLLwy78pFj9Be9gLmiMJFoIinrggQdwKlcQLRcs_eDIid2loLRCppTmlBspGNujJGdcaYwaFCqSKp8bMMQiSO5ZchdVGA_7foMDyecd3AAuZqnOqypCM1_YVSrvqoltme5H5dmtodZSc5RECK5SI8o9Cl4ybDrNTot2nQ0ZczJP5QduMQL3ioMO0YGkzjNnvCGBHykpXYpVAn1F_yPoTeCodLve5UJpIVWSjdroz_VXnMayXdRV4csIdlluDUMdI9yqAD7wHDghCJpqAUKEwEjuKMV9E-CorYl-mp29wWBwe3V_j_17eo4XjPTx5u4uTVL5QZu8ccbaT0623vjnhn3XZgczHWb_Tf0Ps-Pw0XRwfBzXgDQdGNZLB9YYl_6zJeAIOshNGg4kEpXrmM3L_oNu9ZpNV7OXxfNVfIDR425ws-j9Bj8KECE!/

Tomková, A., Gonos, J., Čulková, K., & Rovňák, M. (2024). The Impact of the COVID-19 Pandemic on the Economy of the Slovak Republic. Economies, 12(2), 27.

World Bank. (2020, June 18). Simulating the potential impacts of the COVID-19 school closures on schooling and learning outcomes: A set of global estimates. https://www.worldbank.org/en/topic/education/publication/simulating-potential-impacts-of-covid-19-school-closures-learning-outcomes-a-set-of-global-estimates

## Annex

### Graphs

Graph 1: Gross Domestic Product of Slovakia

Source 1: Statistical Office of the Slovak Republic (2025a)

Graph 2: Slovak Macroeconomic Performance between 1993 and 2023

Source 2: Ibrahim & Ozturk Ofluoglu (2025)

Graph 3: Visitors in tourism accommodation facilities 2017-2022

Source 4: Petrikovičová et al. (2023)

Graph 4: Nominal input of tourism

Source 5: Statistical office of the Slovak Republic (2025b)

Graph 5: Spillover beneficiaries EU comparision

Source 6: European Commission (2025)

Graph 6: Spillovers of RRF allocation

Source 7: European Commission (2025)

### Tables

Table 1: Main macroeconomic indicators of Slovak Republic

|  | 2018 | 2019 | 2020 | 2021 |
| --- | --- | --- | --- | --- |
| GDP growth (% y/y) | 4.0 | 2.5 | -3.4 | 3.0 |
| HICP inflation (% avg.) | 2.5 | 2.8 | 2.0 | 2.8 |
| Government balance (% of GDP) | -1.0 | -1.2 | -5.4 | -5.5 |
| Current account balance (% of GDP) | -2.2 | -3.3 | 0.4 | -1.9 |
| Net FDI (% of GDP) | -1.3 | -2.3 | 2.0 | 0.3 |
| External debt (% of GDP) | 114.3 | 111.7 | 118.7 | 135.1 |
| General government gross debt (% of GDP) | 49.4 | 48.0 | 58.9 | 62.2 |
| Unemployment rate (20-64, %) | 6.3 | 5.6 | 6.5 | 6.7 |
| Nominal GDP (€ billion) | 89.9 | 94.4 | 93.4 | 98.5 |

Source: Eurostat from European Bank for Reconstruction and Development (2022), 
table made by author

Legend:

- risk that the milestone/target will not be met

- delay in the milestone/target, expected to be completed before submission of the payment  
  request

- completed

- on track/according to plan

Table 2: 7th payment request of Slovakia: Milestones Semafor

|  | Milestones / targets | Component |  |
| --- | --- | --- | --- |
|  | Increasing the capacity of the Slovak Environmental Inspectorate | C4 |  |
|  | Amended F departments | C6 |  |
|  | Removal of architectural barriers in secondary schools | C6 |  |
|  | Number of hospitals integrated into the central management system | C11 |  |
|  | Establishment of a single mental health entity and extension of the competences of the association of psychologists | C12 |  |
|  | Number of persons having completed professional training in the field of mental health care | C12 |  |
|  | Expansion and renewal of home nursing care | C13 |  |
|  | Expansion and renewal of the network of mobile hospices (indicator: number of providers of new and refurbished hospices) | C13 |  |
|  | Application of the “1 in – 2 out” rule, the principle of protection against unjustified gold-plating and ex post evaluation of existing regulation | C14 |  |
|  | Entry into force of legislative and procedural changes | RePowerEU |  |
|  | Assessment of trajectories for sustainable use of biomass and biomass supply in Slovakia | RePowerEU |  |
|  | Strategy for the management of state administration buildings | RePowerEU |  |
|  | Extent of renovated floor area of police buildings with a view to reducing the energy intensity of the buildings (in m²) | C16 |  |
|  | Public calls for the establishment of new primary care outpatient clinics | C11 |  |
|  | Digitalisation of residence permit procedures with the aim of simplifying procedures for the public | C16 |  |
|  | Modernisation of court IT equipment for court staff | C15 |  |
|  | Number of hackathons organised | C17 |  |
|  | Measures to support the deployment of hydrogen | RePowerEU |  |

Source: Plán Obnovy (n.d.-c), table made by author

### Figures

Figure 1: Comparison of the number of days schools were partially or completely closed in 2020

Source: Petrikovičová et al. (2023)

Figure 2: Grants allocated so far under RRF

Source: European Commission (n.d.-c)

Figure 3: Reforms ratio and division in Slovakia's NRRP

Source 8: European Commission (2025)

For graphical depiction GDP trend see Graph 1, Annex

Please note: numbers of GDP growth can differ based on methodology

For graphical depiction of Slovak macroeconomic performance see Graph 2, Annex

For table of trends of main macroeconomic indicators see Table 1, Annex

For graphical depiction tourism see Graph 3, Annex

For graphical depiction nominal imput tourism see Graph 4, Annex

For graphical depiction school closures see Figure 1, Annex

For graphical depiction see Figure 2, Annex.

Plán Obnovy (from Slovak Language) is National Recovery and Resilience Plan

See Graph 6, Annex.

See Graph 7, Annex

See Figure 3, Annex

To see detailed NIKA evaluation of the 7th payment request see Table 2, Annex.