## Sheet 3 QTDIAN
Status ID 1 : Under Consideration, 2 : In Planning but not permitting, 3 : In permitting, 4 : Under Construction 6: completed | Progress of the investment since TYNDP2018 | Type of Element | Total route length (km) | Status of projects | Number of projects | % of projects | Progress of the transmission investment since TYNDP2018 | Number of projects | % of projects | Delays during: | Number of projects | % of projects | Progress of the transmission investment since TYNDP2018, without new investments | Number of projects | % of projects | Under construction only | Number of projects | % of projects all | Under permission only | Number of projects | % of projects all | Only AC/DC transmission lines | Number of projects | % of projects all
2 | Ahead of time | ACTransmissionLine | 122 | Under consideration | 95 | 29.595 | Ahead of time | 7 | 2.1807 | Consideration | 6 | 10.7143 | Ahead of time | 7 | 2.9412 | Ahead of time | 2 | 3.3333 | Ahead of time | 3 | 3.5714 | Ahead of time | 7 | 3.4483
2 | Ahead of time | ACTransmissionLine | 157 | Planned but not yet permitting | 82 | 25.5452 | Cancelled | 1 | 0.31153 | Planning but not yet permitting | 4 | 7.1429 | Cancelled | 1 | 0.42017 | Cancelled | 0 | 0 | Cancelled | 0 | 0 | Cancelled | 1 | 0.49261
3 | Ahead of time | ACTransmissionLine | 131 | Permitting | 82 | 25.5452 | Rescheduled | 41 | 12.7726 | Permitting | 31 | 55.3571 | Rescheduled | 41 | 17.2269 | Rescheduled | 32 | 53.3333 | Rescheduled | 11 | 13.0952 | Rescheduled | 0 | 0
3 | Ahead of time | ACTransmissionLine | 83 | Under construction | 61 | 19.0031 | Delayed | 56 | 17.4455 | Construction | 15 | 26.7857 | Delayed | 56 | 23.5294 | Delayed | 15 | 25 | Delayed | 33 | 39.2857 | Delayed | 56 | 27.5862
3 | Ahead of time | ACTransmissionLine | 30 | Completed | 1 | 0.31153 | Investment on time | 123 | 38.3178 | n/a |  | 0 | Investment on time | 123 | 51.6807 | Investment on time | 6 | 10 | Investment on time | 32 | 38.0952 | Investment on time | 112 | 55.1724
4 | Ahead of time | ACTransmissionLine | 87 |  | 321 |  | New investments | 83 | 25.8567 |  | 56 |  | n/a | 10 | 4.2017 | New investments | 4 | 6.6667 | New investments | 5 | 5.9524 | New investments | 27 | 13.3005
4 | Ahead of time | ACTransmissionLine | 159 |  |  |  | n/a | 10 | 3.1153 |  |  |  |  | 238 |  | n/a | 1 | 1.6667 | n/a | 0 | 0 | n/a | 0 | 0
1 | Cancelled | ACTransmissionLine | 76 |  |  |  |  | 321 | [8 empty] | 60 |  |  | 84 |  |  | 203
1 | Delayed | ACTransmissionLine | 0
1 | Delayed | ACTransmissionLine | 2
1 | Delayed | ACTransmissionLine | 170
1 | Delayed | ACTransmissionLine | 72
1 | Delayed | ACTransmissionLine | 40
1 | Delayed | ACTransmissionLine | 40
2 | Delayed | ACTransmissionLine | 65
2 | Delayed | ACTransmissionLine | 0
2 | Delayed | ACTransmissionLine | 350
2 | Delayed | ACTransmissionLine | 32
3 | Delayed | ACTransmissionLine | 140.21
3 | Delayed | ACTransmissionLine | 120.5
3 | Delayed | ACTransmissionLine | 138
3 | Delayed | ACTransmissionLine | 160
3 | Delayed | ACTransmissionLine | 140
3 | Delayed | ACTransmissionLine | 51
3 | Delayed | ACTransmissionLine | 45.2
3 | Delayed | ACTransmissionLine | 109
3 | Delayed | ACTransmissionLine | 100
3 | Delayed | ACTransmissionLine | 14
3 | Delayed | ACTransmissionLine | 64
3 | Delayed | ACTransmissionLine | 45.4
3 | Delayed | ACTransmissionLine | 87.1
3 | Delayed | ACTransmissionLine | 124
3 | Delayed | ACTransmissionLine | 106.6
3 | Delayed | ACTransmissionLine | 90
3 | Delayed | ACTransmissionLine | 95
3 | Delayed | ACTransmissionLine | 11
3 | Delayed | ACTransmissionLine | 22.5
3 | Delayed | ACTransmissionLine | 80
3 | Delayed | ACTransmissionLine | 117
3 | Delayed | ACTransmissionLine | 60
3 | Delayed | ACTransmissionLine | 200
3 | Delayed | ACTransmissionLine | 156
3 | Delayed | ACTransmissionLine | 178
3 | Delayed | ACTransmissionLine | 151
3 | Delayed | ACTransmissionLine | 274
3 | Delayed | ACTransmissionLine | 80
3 | Delayed | ACTransmissionLine | 133
3 | Delayed | ACTransmissionLine | 60
3 | Delayed | ACTransmissionLine | 168
4 | Delayed | ACTransmissionLine | 131
4 | Delayed | ACTransmissionLine | 116
4 | Delayed | ACTransmissionLine | 60
4 | Delayed | ACTransmissionLine | 95
4 | Delayed | ACTransmissionLine | 182
4 | Delayed | ACTransmissionLine | 151
4 | Delayed | ACTransmissionLine | 49
4 | Delayed | ACTransmissionLine | 30
4 | Delayed | ACTransmissionLine | 128
4 | Delayed | ACTransmissionLine | 14
4 | Delayed | ACTransmissionLine | 110
4 | Delayed | ACTransmissionLine | 110
4 | Delayed | ACTransmissionLine | 48
4 | Delayed | ACTransmissionLine | 205
4 | Delayed | ACTransmissionLine | 175
1 | Investment on time | ACTransmissionLine | 11
1 | Investment on time | ACTransmissionLine | 91
1 | Investment on time | ACTransmissionLine | 46.2
1 | Investment on time | ACTransmissionLine | 25
1 | Investment on time | ACTransmissionLine | 47.8
1 | Investment on time | ACTransmissionLine | 70
1 | Investment on time | ACTransmissionLine | 90
1 | Investment on time | ACTransmissionLine | 120
1 | Investment on time | ACTransmissionLine | 1
1 | Investment on time | ACTransmissionLine | 1
1 | Investment on time | ACTransmissionLine | 0
1 | Investment on time | ACTransmissionLine | 2
1 | Investment on time | ACTransmissionLine | 60
1 | Investment on time | ACTransmissionLine | 12
1 | Investment on time | ACTransmissionLine | 950
1 | Investment on time | ACTransmissionLine | 90
1 | Investment on time | ACTransmissionLine | 80
1 | Investment on time | ACTransmissionLine | 70
1 | Investment on time | ACTransmissionLine | 78
1 | Investment on time | ACTransmissionLine | 35.512
1 | Investment on time | ACTransmissionLine | 38.8
1 | Investment on time | ACTransmissionLine | 69.12
1 | Investment on time | ACTransmissionLine | 57
1 | Investment on time | ACTransmissionLine | 90
1 | Investment on time | ACTransmissionLine | 105
1 | Investment on time | ACTransmissionLine | 150
1 | Investment on time | ACTransmissionLine | 130
1 | Investment on time | ACTransmissionLine | 50.6
1 | Investment on time | ACTransmissionLine | 80
1 | Investment on time | ACTransmissionLine | 90
1 | Investment on time | ACTransmissionLine | 21
1 | Investment on time | ACTransmissionLine | 165
1 | Investment on time | ACTransmissionLine | 420
1 | Investment on time | ACTransmissionLine | 220
2 | Investment on time | ACTransmissionLine | 60
2 | Investment on time | ACTransmissionLine | 47
2 | Investment on time | ACTransmissionLine | 16
2 | Investment on time | ACTransmissionLine | 36
2 | Investment on time | ACTransmissionLine | 1
2 | Investment on time | ACTransmissionLine | 40
2 | Investment on time | ACTransmissionLine | 90
2 | Investment on time | ACTransmissionLine | 100
2 | Investment on time | ACTransmissionLine | 123
2 | Investment on time | ACTransmissionLine | 72
2 | Investment on time | ACTransmissionLine | 48
2 | Investment on time | ACTransmissionLine | 68
2 | Investment on time | ACTransmissionLine | 203
2 | Investment on time | ACTransmissionLine | 75
2 | Investment on time | ACTransmissionLine | 57.11
2 | Investment on time | ACTransmissionLine | 119
2 | Investment on time | ACTransmissionLine | 41.5
2 | Investment on time | ACTransmissionLine | 288.5
2 | Investment on time | ACTransmissionLine | 77
2 | Investment on time | ACTransmissionLine | 70
2 | Investment on time | ACTransmissionLine | 95
2 | Investment on time | ACTransmissionLine | 135
2 | Investment on time | ACTransmissionLine | 65
3 | Investment on time | ACTransmissionLine | 243
3 | Investment on time | ACTransmissionLine | 234
3 | Investment on time | ACTransmissionLine | 147
3 | Investment on time | ACTransmissionLine | 92
3 | Investment on time | ACTransmissionLine | 60
3 | Investment on time | ACTransmissionLine | 70
3 | Investment on time | ACTransmissionLine | 90
3 | Investment on time | ACTransmissionLine | 19
3 | Investment on time | ACTransmissionLine | 290
3 | Investment on time | ACTransmissionLine | 100
3 | Investment on time | ACTransmissionLine | 0
3 | Investment on time | ACTransmissionLine | 32
3 | Investment on time | ACTransmissionLine | 35
3 | Investment on time | ACTransmissionLine | 50
3 | Investment on time | ACTransmissionLine | 94
3 | Investment on time | ACTransmissionLine | 100
3 | Investment on time | ACTransmissionLine | 147
3 | Investment on time | ACTransmissionLine | 80
3 | Investment on time | ACTransmissionLine | 50
3 | Investment on time | DCTransmissionLine | 0
3 | Investment on time | DCTransmissionLine | 165
3 | Investment on time | DCTransmissionLine | 700
3 | Investment on time | DCTransmissionLine | 200
3 | Investment on time | DCTransmissionLine | 540
3 | Investment on time | DCTransmissionLine | 300
3 | Investment on time | DCTransmissionLine | 300
3 | Investment on time | DCTransmissionLine | 373
3 | Investment on time | DCTransmissionLine | 340
3 | Investment on time | OffshoreDCTransmissionCable | 220
3 | Investment on time | OffshoreDCTransmissionCable | 665
3 | Investment on time | OffshoreDCTransmissionCable | 240
3 | Investment on time | OffshoreDCTransmissionCable | 370
4 | Investment on time | ACTransmissionLine | 15
4 | Investment on time | ACTransmissionLine | 108
4 | Investment on time | ACTransmissionLine | 30
4 | Investment on time | ACTransmissionLine | 86
4 | Investment on time | ACTransmissionLine | 150
4 | Investment on time | ACTransmissionLine | 60
4 | Investment on time | ACTransmissionLine | 300
4 | Investment on time | ACTransmissionLine | 30
4 | Investment on time | ACTransmissionLine | 60
4 | Investment on time | ACTransmissionLine | 27
4 | Investment on time | ACTransmissionLine | 125
4 | Investment on time | ACTransmissionLine | 18
4 | Investment on time | ACTransmissionLine | 80
4 | Investment on time | ACTransmissionLine | 210
4 | Investment on time | ACTransmissionLine | 139
4 | Investment on time | ACTransmissionLine | 161
4 | Investment on time | ACTransmissionLine | 179
4 | Investment on time | ACTransmissionLine | 80
4 | Investment on time | ACTransmissionLine | 26
4 | Investment on time | ACTransmissionLine | 75
4 | Investment on time | ACTransmissionLine | 13
4 | Investment on time | ACTransmissionLine | 40
4 | Investment on time | ACTransmissionLine | 40
4 | Investment on time | DCTransmissionLine | 90
4 | Investment on time | DCTransmissionLine | 69
4 | Investment on time | DCTransmissionLine | 445
4 | Investment on time | OffshoreACTransmissionCable | 24
4 | Investment on time | OffshoreDCTransmissionCable | 623
4 | Investment on time | OffshoreDCTransmissionCable | 720
4 | Investment on time | OffshoreDCTransmissionCable | 770
4 | Investment on time | OnshoreSubstation | 0
4 | Investment on time | OnshoreSubstation | 0
4 | Investment on time | OnshoreSubstation | 0
6 | Investment on time | ACTransmissionLine | 41
1 | New Investment | DCTransmissionLine | 150
1 | New Investment | DCTransmissionLine | 700
1 | New Investment | DCTransmissionLine | 0
1 | New Investment | DCTransmissionLine | 180
1 | New Investment | DCTransmissionLine | 1373
1 | New Investment | DCTransmissionLine | 110
1 | New Investment | DCTransmissionLine | 170
1 | New Investment | OffshoreACTransmissionCable | 81
1 | New Investment | OffshoreACTransmissionCable | 14
1 | New Investment | OffshoreACTransmissionCable | 34
1 | New Investment | OffshoreACTransmissionCable | 14
1 | New Investment | OffshoreACTransmissionCable | 170
1 | New Investment | OffshoreACTransmissionCable | 31
1 | New Investment | OffshoreDCTransmissionCable | 1270
1 | New Investment | OffshoreDCTransmissionCable | 180
1 | New Investment | OffshoreDCTransmissionCable | 170
1 | New Investment | OffshoreDCTransmissionCable | 330
1 | New Investment | OffshoreDCTransmissionCable | 0
1 | New Investment | OffshoreDCTransmissionCable | 300
1 | New Investment | OffshoreDCTransmissionCable | 245
1 | New Investment | OffshoreDCTransmissionCable | 250
1 | New Investment | OffshoreDCTransmissionCable | 328
1 | New Investment | OffshoreDCTransmissionCable | 360
1 | New Investment | OffshoreDCTransmissionCable | 290
1 | New Investment | OffshoreDCTransmissionCable | 390
1 | New Investment | OffshoreDCTransmissionCable | 400
1 | New Investment | OffshoreDCTransmissionCable | 490
1 | New Investment | OffshoreDCTransmissionCable | 133
1 | New Investment | OffshoreDCTransmissionCable | 450
1 | New Investment | OffshoreDCTransmissionCable | 230
1 | New Investment | OffshoreDCTransmissionCable | 610
1 | New Investment | OffshoreDCTransmissionCable | 640
1 | New Investment | OffshoreDCTransmissionCable | 195
1 | New Investment | OffshoreDCTransmissionCable | 125
1 | New Investment | OffshoreDCTransmissionCable | 1070
1 | New Investment | OffshoreDCTransmissionCable | 200
1 | New Investment | OffshoreDCTransmissionCable | 1330
1 | New Investment | OffshoreDCTransmissionCable | 600
1 | New Investment | OffshoreSubstation | 0
1 | New Investment | OffshoreSubstation | 40
2 | New Investment | ACTransmissionLine | 160
2 | New Investment | ACTransmissionLine | 140
2 | New Investment | ACTransmissionLine | 175
2 | New Investment | ACTransmissionLine | 67
2 | New Investment | ACTransmissionLine | 83
2 | New Investment | ACTransmissionLine | 58
2 | New Investment | ACTransmissionLine | 61
2 | New Investment | ACTransmissionLine | 110
2 | New Investment | ACTransmissionLine | 70
2 | New Investment | ACTransmissionLine | 80
2 | New Investment | ACTransmissionLine | 180
2 | New Investment | ACTransmissionLine | 170
2 | New Investment | ACTransmissionLine | 105
2 | New Investment | DCTransmissionLine | 255
2 | New Investment | DCTransmissionLine | 267
2 | New Investment | DCTransmissionLine | 407
2 | New Investment | DCTransmissionLine | 230
2 | New Investment | DCTransmissionLine | 225
2 | New Investment | DCTransmissionLine | 211
2 | New Investment | OffshoreDCTransmissionCable | 195
2 | New Investment | OffshoreDCTransmissionCable | 900
2 | New Investment | OffshoreDCTransmissionCable | 400
2 | New Investment | OffshoreDCTransmissionCable | 370
2 | New Investment | OffshoreDCTransmissionCable | 156
2 | New Investment | OffshoreSubstation | 50
2 | New Investment | OnshoreACTransmissionCable | 25
2 | New Investment | OnshoreACTransmissionCable | 25
2 | New Investment | OnshoreACTransmissionCable | 25
2 | New Investment | OnshoreACTransmissionCable | 20
2 | New Investment | OnshoreSubstation | 0
2 | New Investment | OnshoreSubstation | 0
2 | New Investment | OnshoreSubstation | 0
2 | New Investment | OnshoreSubstation | 0
2 | New Investment | OnshoreSubstation | 0
3 | New Investment | OffshoreDCTransmissionCable | 500
3 | New Investment | OffshoreDCTransmissionCable | 400
3 | New Investment | OffshoreDCTransmissionCable | 300
3 | New Investment | OffshoreDCTransmissionCable | 700
3 | New Investment | OffshoreDCTransmissionCable | 310
4 | New Investment | OnshoreSubstation | 0
4 | New Investment | OnshoreSubstation | 0
4 | New Investment | OnshoreSubstation | 0
4 | New Investment | OnshoreSubstation | 0
1 | Rescheduled | OnshoreACTransmissionCable | 16
1 | Rescheduled | OnshoreSubstation | 0
1 | Rescheduled | OnshoreSubstation | 0
1 | Rescheduled | OnshoreSubstation | 0
1 | Rescheduled | OnshoreSubstation | 0
1 | Rescheduled | OnshoreSubstation | 0
2 | Rescheduled | OnshoreSubstation | 0
2 | Rescheduled | OnshoreSubstation | 0
2 | Rescheduled | OnshoreSubstation | 0
2 | Rescheduled | OnshoreSubstation | 0
2 | Rescheduled | OnshoreSubstation | 0
2 | Rescheduled | OnshoreSubstation | 0
2 | Rescheduled | OnshoreSubstation | 0
2 | Rescheduled | OnshoreSubstation | 0
2 | Rescheduled | OnshoreSubstation | 0
2 | Rescheduled | OnshoreSubstation | 0
2 | Rescheduled | OnshoreSubstation | 0
2 | Rescheduled | OnshoreSubstation | 0
2 | Rescheduled | OnshoreSubstation | 0
2 | Rescheduled | PhaseShiftingTransformer | 0
2 | Rescheduled | PhaseShiftingTransformer | 0
2 | Rescheduled | ReactiveCompensationDevice | 1200
2 | Rescheduled |  | 0
2 | Rescheduled |  | 0
3 | Rescheduled | OffshoreDCTransmissionCable | 898
3 | Rescheduled | OnshoreSubstation | 0
3 | Rescheduled | OnshoreSubstation | 0
3 | Rescheduled | OnshoreSubstation | 0
3 | Rescheduled | OnshoreSubstation | 0
3 | Rescheduled | OnshoreSubstation | 0
3 | Rescheduled | OnshoreSubstation | 0
3 | Rescheduled | Transformer | 0
3 | Rescheduled |  | 0
3 | Rescheduled |  | 0
3 | Rescheduled |  | 0
4 | Rescheduled | PhaseShiftingTransformer | 0
4 | Rescheduled | PhaseShiftingTransformer | 0
4 | Rescheduled | PhaseShiftingTransformer | 10
4 | Rescheduled | ReactiveCompensationDevice | 0
4 | Rescheduled | Transformer | 0
4 | Rescheduled |  | 0
1 |  | OnshoreSubstation | 0
1 |  | PhaseShiftingTransformer | 0
1 |  | PhaseShiftingTransformer | 0
1 |  | ReactiveCompensationDevice | 0
1 |  | ReactiveCompensationDevice | 0
1 |  | Transformer | 0
1 |  |  | 0
1 |  |  | 0
2 |  |  | 0
4 |  |  | 0