## Slide 1: EMI Structure, Plans, Deliverables
Alberto Di Meglio (CERN)
Project Director
ATLAS Software & Computing Week
Geneva, 21 July 2011

## Slide 2: What is EMI?
21/07/2011
ATLAS Software & Computing Week
<number>
European Middleware Initiative
Collaboration among the four major European middleware providers
Three-year project, 24 M EUR, 50% from the European Commission, 50% from the partner Institutes
26 partners
Work in three major areas:
  Consolidation of common libraries, clients, interfaces across the four MW stacks, decommissioning of unused services
  Development of new functionality based on user requirements
  User support

## Slide 3: Partners (26)
21/07/2011
ATLAS Software & Computing Week
<number>

## Slide 4: EMI Middleware Evolution
EMI Baseline Services
Applications Integrators, System Administrators
21/07/2011
ATLAS Software & Computing Week
<number>
Users and infrastructure requirements,
Standards, New technologies
3 years
Before EMI
After EMI
Specialized services, professional support and customization
Standard interfaces
Standard interfaces

## Slide 5: EMI Release and Software Timeline
21/07/2011
ATLAS Software & Computing Week
<number>
01/05/2010
Start
EMI 1
EMI 2
EMI 3
Support & Maintenance
Support & Maintenance
Support & Maintenance
Supp. & Maint.
30/04/2011
30/04/2012
28/02/2013
Major releases
Released May 12th

## Slide 6: Technical Areas and PTs
21/07/2011
ATLAS Software & Computing Week
<number>
ARC CE, UNICORE Services, gLite MPI , gLite Compute, etc
dCache, CERN Data, DGAS, StoRM ,etc
ARC Container, UNICORE Security, Cesnet Security, Argus, VOMS, etc
ARC Infosys, APEL client, DGAS Client, gLite Infosys, EMI Registry, etc
Product Teams
Dedicate teams of experts
Fully responsible for development, maintenance and unit/system testing

## Slide 7: Collaborations
DCI Roadmap
21/07/2011
ATLAS Software & Computing Week
<number>
EMI
EGI, PRACE, WLCG,OSG, etc.
ESFRI,
VRCs
StratusLab
VENUS-C
EDGI
Requirements
Releases
Requirements Collaborations
IGE
SLAs &
Support
Standards,
Industry
Requirements Collaborations
EGI-InSPIRE

## Slide 8: Requirements management
Sources of requirements
  EGI-TCB: formal requests communicated via EGI Tracker
  WLCG: requests communicated via various channels (MB, GDB, existing trackers)
  Users: direct communication with PTs
Handling of requirements
  After an initial filtering requests are recorded in the EMI Req. Tracker
  PTB assesses, categorizes and prioritizes requirements
  Endorsed requests are translated into objectives, then to development tasks
  Continous process, though requirements may not have an immediate effect on workplan
Everything is recorded, monitored and tracked:
  https://savannah.cern.ch/task/?group=emi-req
21/07/2011
ATLAS Software & Computing Week
<number>

## Slide 9: High-level Technical Roadmap
21/07/2011
ATLAS Software & Computing Week
<number>

## Slide 10: Technical Objectives DNA1.3.1
21/07/2011
ATLAS Software & Computing Week
ID | Description | Components / Results | Deadline | Achieved
C1 | Glue 2.0 support in job management services and client tools. | A-REX, CREAM, UNICORE Services Environments, UCC, WMS, arc*, arclib_client | M12 | 3/6 - 50% achieved (not WMS and no clients yet), all clients in Y2
D1 | All storage elements publishing initial GLUE 2.0 storage information | dCache, DPM, StoRM | M12 | 3/3 100 % achieved
D2 | Using https instead of httpg for the SRM protocol as a prototype implementation in one storage element and client (library) | dCache server and client | M12 | 2/2 100 % achieved
D3 | All storage elements offering support for the http(s) protocol | dCache, DPM, StoRM | M12 | 3/3 100 % achieved
D4 | All storage elements offering at least a prototype-level support for the "file://" access protocol | dCache, DPM, StoRM | M12 | 3/3 100 % achieved
D5 | File Catalogue Access from UNICORE | UNICORE Services Environment | M12 | 0.75/1 Prototype existing 75% achieved
S1 | Agreement on a minimal common set of security attributes to be used in policies | XACML Policy Agreement | M12 | 1/1 100% achieved
I1 | Provide early internal guidelines for integrating messaging into potential EMI target components | Guidelines exists | M10 | 1/1 100% achieved
I2 | Design a common EMI service registry that is required in order to discover all the service endpoints of the different middleware components | EMI Service Registry Design exists | M10 | 1/1 100% achieved
I3 | Investigate possible use cases for a common standard messaging system in the accounting area | Initial Use Case Survey exists | M12 | 0.75/1 75% achieved
I4 | Investigate possible use cases for a common standard messaging system for the service monitoring and management | Only initial studies | M12 | 0.5/1 50% achieved
I5 | Investigate possible use cases for a common standard messaging system for the information services and L&B | Use Case Survey exists | M12 | 1/1 100% achieved
<number>

## Slide 11: Year 2 top technical priorities (1/2)
Compute:
  EMI Execution Service: implementation of the agreed common job management methods
  GLUE2 support in compute clients
Data:
  Client-side GLUE2 support implementation
  EMI Data Access Library design and implementation
  Storage Element and Catalogue synchronization
Security:
  Simplified management of security credentials (AAI)
  EMI Authentication Library implementation
  EMI delegation agreement
21/07/2011
ATLAS Software & Computing Week
<number>

## Slide 12: Year 2 top technical priorities (2/2)
Infrastructure:
  EMI service registry implementation
  Cloud strategy definition
  Delivery of service monitoring via NAGIOS for all services
All:
  Consolidation plans (removal of duplicate and obsolete components)
  Port to SL6 and Debian
  Usability improvements
    Command line parameters
    Error messages
21/07/2011
ATLAS Software & Computing Week
<number>

## Slide 13: User Support
21/07/2011
ATLAS Software & Computing Week
<number>
GGUS used as single entry point
Dedicated Support Unit for each Product or sets of related Products

## Slide 14: Timeline
July 2011: Development plan details defined, Product Teams start working on new major functionality
Dec 2011: Beta versions of all new services and functionality
April 2012: EMI 2
Continuous activity: bug fixing, release of minor, backward compatible features depending on user needs (independent service releases)
21/07/2011
ATLAS Software & Computing Week
<number>

## Slide 15: Useful links
  EMI Web Site http://www.eu-emi.eu
  Y2 Technical Plan http://cdsweb.cern.ch/record/1277543/files/EMI-DNA1.3.2-1277543-Technical_Development_Plan-v1.0.pdf
  Requirements Tracker https://savannah.cern.ch/task/?group=emi-req
  EMI Software Repository http://emisoft.web.cern.ch/emisoft
  EMI Documentation http://www.eu-emi.eu/en/emi-1-kebnekaise-docs
  GGUS (for submitting bugs and new requirements) https://ggus.org/pages/home.php
  Announce mailing list http://mail.eu-emi.eu/mailman/listinfo/emi-announce
21/07/2011
ATLAS Software & Computing Week
<number>

## Slide 16: Thank you
21/07/2011
<number>
ATLAS Software & Computing Week
EMI is partially funded by the European Commission under Grant Agreement INFSO-RI-261611