## Slide 1: AURORA SDG DASHBOARD FOR RESEARCH
DEMONSTRATING THE SOCIETAL INFLUENCE OF OUR RESEARCH
http://bit.ly/aurora-sdg
2nd of March 2021 | UBVU MT| Maurice Vanderfeesten | Vrije Universiteit Amsterdam | Twitter: @maurice_
Photo by: Cpl. Jesus Sepulveda Torres https://www.mcbhawaii.marines.mil/Photos/igphoto/2001813560/

## Slide 2: Agenda
  Current SDG demo dashboard
  progress of the SDG project
  Partnership with Elsevier
  MoU with OpenAIRE

## Slide 3: MEET OUR PROJECT TEAM | TASK 5.1: SDG RESEARCH DASHBOARD (ONE OF THE 20+ PROJECT TEAMS IN THIS UNIVERSITY ALLIANCE)
112
Faculties
260.000
Students
30.000
Staff
673.922
Alumni
813
Research Groups
UNITING
Work package 5: Aurora Sustainability Pioneers
Task 5.2 Aurora Sustainability Education
Task 5.3 Aurora Sustainable Campus
Action plan ASCA
Task 5.1 Aurora SDG Research Dashboard

## Slide 4: 5.1 AURORA SDG RESEARCH DASHBOARD WHAT IS THE OBJECTIVE WITH THIS TASK?
To turn the SDGs into a leading narrative for research in the Aurora Alliance.
Results in 2023:
The SDG Research Dashboard to become a robust and operational tool.
The SDG Research Dashboard is available for other universities and networks.
Chairs
Task 5.2 Aurora Sustainability Education
Task 5.3 Aurora Sustainable Campus
Action plan ASCA
Task 5.1 Aurora SDG Research Dashboard

## Slide 5: CURRENT SDG-RESEARCH DASHBOARD BASED ON KEYWORD SEARCHES
https://bit.ly/aurora-sdg-dashboard-v3

## Slide 6: POTENTIAL: DISCOVER WHAT EXCELLENT RESEARCH IS UNKNOW TO POLICY MAKERS

## Slide 7: PROJECT TIMELINE
Task 5.1 Aurora SDG Research Dashboard
More at https://alliance.aurora-network.global/work-packages/aurora-sdg-research-dashboard/
Source: https://sites.google.com/vu.nl/aurora-sdg-research-dashboard/deliverables
WE
ARE
HERE
SHOULD
BE
HERE

## Slide 8: D1: Evaluation of the AURORA SDG QUERIES v5 | DONE
Average Recall: 14%
Average
Precision: 70%
v4
v5
Accuracy (F1-score) of the queries increased 5% after feedback Survey from 244 Senior Researchers. doi:10.5281/zenodo.3813230 (608 views, 195 downloads on 2021-11-12)
Precision: 70% of the papers found by the queries were in fact related to the evaluated SDG, according to the Aurora researchers.
      Meaning; a 70% chance a paper is related to an SDG using the Aurora SDG Queries v5.
Recall: 14% of the papers suggested by Aurora researchers were found back in the SDG result sets of the queries.
      Meaning; the Aurora SDG queries v5 miss 86% of the papers that are related to an SDG.
Tradeoff: The higher the Recall, the lower the Precision will be.
Advantage: High Precision data can be used to train machine learning models.
Further reading: Evaluation report doi:10.5281/zenodo.4917107 (213 views, 92 downloads on 2021-11-12)

## Slide 9: D2: SDG text classification model (multi-lingual) | ALMOST DONE
1.4 million abstracts used to train machine learning models doi:10.5281/zenodo.5224005 (views 68, downloads 101 on 2021-11-12)
Using High Performance Computing (GPU’s) facilities and budget from University of South Denmark, in partnership with Elsevier
Trained 169 multi-language models (for each SDG-Target) with high accuracy scores (>95%). Uploaded soon on https://zenodo.org/communities/aurora-universities-network/
Evaluation Report at end of year doi:10.5281/zenodo.5603019 (placeholder)

## Slide 10: D3: SDG CLASSIFICATION SERVICE | NEXT UP
MOCKUP

## Slide 11: ELSEVIER PARTNERSHIP | almost ending
  https://www.elsevier.com/about/partnerships/sdg-research-mapping-initiative
  Our goals:
    👍Transparent about quality? Pushing market to adopt Aurora standards on transparency,
    👍 Fine grained? … and define queries on target level (but not explicitly)
  Make Aurora SDG queries obsolete and eliminate regular maintenance
    👎Re-Usable? Elsevier queries are not directly re-usable in Scopus. Works only in Elsevier’s back-end system.
    👎 Maintained? Elsevier has no plans to update / maintain the queries.
  Make use of Elsevier’s resources to build a multi-lingual text classifier.
    😕 Data? We got some sample data from Elsevier, but we needed more for machine learning on target level and collected our own 1.4 million abstracts.
    😕 Compute? ended up using HPC resources from University of South Denmark👍, because Elsevier’s Data Lab did not contain abstracts.
  Publishing together a paper on results
    🤞Writing. Elsevier SDG queries (heavy focus) vs Aurora queries vs Aurora text classifier (Queries and ML)

## Slide 12: OpenAIRE | New Partnership
  WHY:
    Mutual benefits;
      align complementary project activities, reaching greater impact than acting in solitude
      Increased visibility, EU projects collaborating.
    OpenAIRE provides:
      Freely available auto-curated (meta)data on Publications, Grants, Datasets, affiliated to Aurora universities beyond Scopus and Web of Science.
      Support on using open standards making institutional repositories OpenAIRE compliant.
      Training on using OpenAIRE Open Science services.
    Aurora provides:
      SDG text classifier knowledge and models to be applied on the OpenAIRE Research Graph
      Metadata content from our institutional repositories
      Sharing Open Science practices

## Slide 13
OpenAIRE is a European project supporting Open Science, and Part of the European Open Science Cloud
On the one hand OpenAIRE is an network of dedicated Open Science experts promoting and providing training on Open Science.
On the other hand OpenAIRE is a technical infrastructure collecting, connecting and re-distributing research output metadata from connected data providers.
OpenAIRE

## Slide 14: OpenAIRE non-profit at a glance
Mission: Establish, maintain and operate an open and sustainable scholarly communication infrastructure and provide the necessary services, resources and network for supporting a common European e-science environment.
Organization:
Non-profit
Incorporated in 2018
36 regular members
11 Associate members
From 34 countries

## Slide 15: OpenAIRE serving Open Science
Guidelines
Setting compliance of EOSC data sources
Research Community Gateways
EOSC scientific product catalogue
Funder - Institution – Community OS Monitoring
Register
Validate
Data Source
OpenAIRE Guidelines
for LITERATURE Repositories v4.0
OpenAIRE Guidelines
for SOFTWARE Repositories
OpenAIRE Guidelines
for CRIS
OpenAIRE Guidelines
for USAGE statistics
OpenAIRE Guidelines
for OTHER research products
OpenAIRE Guidelines
for DATA Repositories
1
3
Global sources
2
4
5

## Slide 16: OpenAIRE Connect | an On-demand Open Research Gateways for research communities
A ”community view” of the OpenAIRE Research Graph (publications, data, grants, software, etc.)
  Available via a web portal, API and dumps published on Zenodo
An Open Science Toolkit: entry point to tools for the implementation of Open Science publishing and FAIR-data practices
Closely collaborating research‑intensive European universities, who use their academic excellence to drive societal change.
MOCKUP

## Slide 17: OpenAIRE Partnership | Memorandum of Understanding (MoU)
  WHAT:
    [M1] GATEWAY: OpenAIRE CONNECT Gateway for Aurora Universities
    [M2] OS-MONITOR: OpenAIRE Open Science Monitoring Dashboard + Aurora Open Science
    [M3] SDG-ADDON: Aurora SDG classifier for Research publications added to gateway and os-monitor
    [M4] OS-ENGAGEMENT: Open Science training, services and best practices
    [M5] Communication

## Slide 18: OpenAIRE Partnership | MoU TIMELINE
M1 Gateway
M2 OS-Monitor
M3 SDG-addon
M4 OS-Engage
DATA
Used in
Aurora SDG project
Used in
Aurora SWAFS project
2021 Q3 Q4 2022 Q1 Q2 Q3 Q4 2023 Q1 Q2
MODELS
M5 Comms
M5 Comms
M5 Comms
M5 Comms
DATA
DATA
Critical path
Aurora
SDG project
Additional paths

## Slide 19: OpenAIRE Partnership | signing MoU
  Obligations?
    No formal undertaking
    Reach goals to the best of our abilities.
  Signing:
    WHO?
      Chair VRR?
      Sec. General?
    WHEN?
      Preferably end of this week.