D.0.4 Minutes of the kickoff meeting 2020

WP0 Project coordination

Responsible Partner: DTU

Contributing partners: ANSES, SSI, UCM, INRA, IP, APHA, ISS, IZSAM, IZSLER, RIVM, WBVR, PIWET, SLV, FOHM, SVA

GENERAL INFORMATION

| European Joint Programme full title | Promoting One Health in Europe through joint actions on foodborne zoonoses, antimicrobial resistance and emerging microbiological hazards |
| --- | --- |
| European Joint Programme acronym | One Health EJP |
| Funding | This project has received funding from the European Union’s Horizon 2020 research and innovation programme under Grant Agreement No 773830. |
| Grant Agreement | Grant agreement n° 773830 |
| Start Date | 01/01/2018 |
| Duration | 60 Months |

DOCUMENT MANAGEMENT

| JIP/JRP deliverable | D.0.4 (JIP IA 2.1-WP0-T1-ST1) |
| --- | --- |
| Project Acronym | EJP CARE |
| Author | Jeppe Boel, SSI and Susanne Karlsmose Pedersen, DTU |
| Other contributors | WP leaders (DTU, SSI, ANSES, IP, |
| Due month of the report | M26 (February 2020) |
| Actual submission month | M29 (May 2020) |
| Type R: Document, report DEC: Websites, patent filings, videos, etc.; OTHER | R Save date: 27-May-20 |
| Dissemination level PU: Public (default) CO: confidential, only for members of the consortium (including the Commission Services) | PU This is the default setting. If this project deliverable should be confidential, please add justification here (may be assessed by PMT): |
| Dissemination Author’s suggestion to inform the following possible interested parties. | OHEJP WP 1 ☐ OHEJP WP 2 ☐ OHEJP WP 3 ☐ OHEJP WP 4 ☒ OHEJP WP 5 ☐ OHEJP WP 6 ☐ OHEJP WP 7 ☐ Project Management Team ☐ Communication Team ☐ Scientific Steering Board ☐ National Stakeholders/Program Owners Committee ☐ EFSA ☐ ECDC ☐ Other international stakeholder(s): ……………………………………………………………………… Social Media: Other recipient(s): |

Mintues - EJP CARE Kickoff meeting 2020

# Participants

All EJP CARE consortium partners were represented at the meeting:

National Food Institute-DTU (EURL-AR) (Denmark), State Serum Institute (Denmark), Istituto Superiore di Sanità (EURL STEC) (Italy), Istituto Zooprofilattico Sperimentale dell’Abruzzo e del Molise “G. Caporale” (IZSAM) (Italy), Istituto Zooprofilattico Sperimentale della Lombardia e dell’Emilia Romagna (IZSLER) (Italy), National Institute for Public Health and Environment (RIVM) (EURL SALM) (the Netherlands), WUR – WBVR (the Netherlands), The Public Health Agency of Sweden (Sweden), National Veterinary Institute (EURL CAMP) (Sweden), Swedish National Food Agency (Sweden), National Veterinary Research Institute, Puławy (NVRI) (Poland), VISAVET – UCM (Spain), ANSES (France), Institut Pasteur (France), French National Institute for Agricultural Research (France), Animal & Plant Health Agency (APHA) (United Kingdom).

Minutes taker: Jeppe Boel, SSI, Denmark

___________________________________________________________________________

Rene S. Hendriksen, DTU, opened the two day meeting by welcoming the meeting participants.

This was followed by a short introduction of the participants/institutions.

The agenda was adapted with the adjustment that Karin Artursson presentation was moved to the last before lunch on February 12. Moez Sanaa (ANSES) was excused from the meeting, and Laurent Guillier, ANSES presented WP4.

12 February 2020 – Day 1

Rene gave an overall introduction to the OH-CARE project and shared the latest information from the OHEJP organization. The review of the project resulted in a number of consensus recommendations from the Scientific Steering Board (SSB). Rene presented these recommendations and this was followed by an in depth discussion. Based on the discussion Rene was given mandate to give feedback to the OHEJP organization on the recommendations. It was decided that Rene will communicate with the WP leads for them to give feedback to (include or reject) the recommendations. Rene gave general information, including information about the dissemination policy, and Rene presented the framework for the management of the project, including reporting to the OHEJP organization. For this purpose Rene presented GANTT charts, and templates for reporting the progress of the four WP’s.

Rene’s presentation was followed by short presentations by the work package leaders. Jeppe Boel, SSI, presented WP1 (Develop cross-sectional PT’s), Olivier Chesneau IP presented WP2 (Creation of EUROpanelOH), Michel-Yves Mistou INRA presented WP3 (Access and sustainability of well-defined microbial reference materials (RM)), and Laurent Guillier, ANSES, presented WP4 (Risk Assessment).

Following the presentations of the EJP CARE WPs, Nadia Boisen, SSI, presented the integrative OHEJP Harmony-Cap (One Health Harmonisation of Protocols for the Detection of Foodborne Pathogens and AMR Determinants) project, and thereafter Uffe Christian Braae, SSI, presented the integrative OHEJP Matrix (Connecting dimensions in OneHealth surveillance) project.

Before lunch, Karin Artursson, SVA, presented OHEJP organization with special emphasis on the work package 4, joint integrative projects. Karin outlined the overall project organization, and told about the dissemination strategy and the expected reporting on the progress in milestones and deliverables.

After lunch, Rene introduced the WP breakout session. The work undertaken in these sessions was discussions and planning of the practical work in the four WPs. Meeting day one ended with a short plenum session, where the progress made during the breakout sessions briefly was presented.

WP1: At the WP1 breakout sessions the discussions were focused on the IA 2.1-WP1-T1: Mapping of existing and proposals for new PT schemes. Lucas Wijnands from RIVM agreed to draft a first outline of the report and circulate this in early April. APHA offered to develop a draft with definitions for the use of subject specific terms. This draft should also be circulated in early April.

Subtask IA 2.1-WP1-T2 were also discussed. For ST1, ST1 Pilot PT on isolation/detection and characterization of pathogens, there was a broad discussion on which methods and bacteria that should have the main attention and it was also discussed whether the samples should contain matrices and how this could be accommodated taking into account the cross sectorial differences. The current ideas for IA 2.1-W1-T2-ST2, Pilot PT on typing/characterization including WGS, were also briefly discussed. For IA 2.1-W1-T2-ST3, Pilot PT on outbreak surveillance based on WGS data, it was decided to focus this exercise on in silico based EQAs.

WP2: The attendees were Henk Aarts (RIVM), Kees Veldman (WUR-WBVR), Valeria Michelacci (ISS), Susanne Karlsmose Pedersen (DTU), Pernille Gymoese (SSI), Nalini Rama Rao (INRAE), Anne Brisabois (ANSES), Monica Ricao Canelhas (SLV), Maria Ugarte Ruiz (VISAVET-UCM), Olivier Chesneau (IP).

Decision was taken to separate the DB of strains and the DB of antimicrobial resistance. The need to better define what is a Reference Material, what would be the inclusion criteria, those mandatory and those optional in the inventory of resources, spent a large part of the time. Specific needs of reference repositories from other EJP projects were mentioned for BioPigee, Adonis, Tox-Detect, DiSCoVeR and ListAdapt. Necessity of a close networking with WP1 and WP4 of CARE for the choice of RM to be prioritized and with WP3 for required fields of the future CARE catalog of RM. It was noticed that seven teams have a Bruker instrument for the future MALDI-TOF characterization.

WP3: For WP3, the discussions that took place during the KO meeting have been rich and meaningful, the main issue at stake was to clarify the objectives linked to the access and sustainability of microbial reference materials and to think of the best way to reach them. The division of tasks was refined into five deliverables and six milestones and the responsibilities of the partners in charge was redefined. The new milestones and deliverables were sent to and approved by the CARE coordination.

WP4: Several milestones were discussed and added to the work program to better described the task 1 related to the survey of data for risk assessment. Additionally, the objectives of the survey were more clearly defined.

13 February 2020 – Day 2

Meeting day two started with a new breakout sessions, where the plans for the practical work were further elaborated. The morning ended with a plenum session, where the outcome of the work in the four WPs presented.  I was agreed that the work should continue and more firm work plans and should be presented to the CARE management group in April 2020.

Finally, there was a general discussion on how to ensure that the activities in the different WPs were coordinated. This included a discussion of the legal basis of the project with regard to both MTA and MOU, and it was agreed that this subject needed further clarification.

Presentations from the meeting are available in the EJP CARE sharepoint site.

Appendix: Agenda from the meeting

---   ---   ---

| Wednesday, 12 February Venue: DTU National Food Institute (Anker Engelunds Vej 1, 2800 Kgs. Lyngby) |  |  |
| --- | --- | --- |
| 9:00 | Meet and greet Overall introduction to the OHEJP project Overall introduction to the EJP CARE project including comments from the Scientific Steering Board (SSB) | Karin Artursson, SVA Rene S. Hendriksen, DTU |
| 10:00 | Coffee break |  |
| 10:15 | Introductions of EJP CARE work packages (15 minutes each) - WP1 – Develop cross-sectional PT’s - WP2 – Creation of EUROpanelOH - WP3 – Access and sustainability of well-defined microbial reference materials (RM) - WP4 – Risk Assessment Other OHEJP projects with which EJP CARE plans to collaborate (15 minutes each) - OHEJP Harmony (One Health Harmonisation of Protocols for the Detection of Foodborne Pathogens and AMR Determinants) - OHEJP Matrix (Connecting dimensions in One-Health surveillance) Time for discussion | Jeppe Boel (SSI) Olivier Chesneau (IP) Michel-Yves Mistou (INRA) Laurent Guillier (ANSES) Nadia Boisen (SSI) Uffe Christian Braae (SSI) |
| 12:15 | Lunch |  |
| 13:15 | Introduction to breakout session Breakout session to plan the work in details. Divided in WP groups and WP leads will be leading the discussions in each group - WP1 - WP2 - WP3 - WP4 | Chair: Rene S. Hendriksen |
| 15:00 | Plenum discussions based on the outcomes of the breakout session – feedback to improve the plans | Chair: Mia Torpdahl |
| 16:00 | End of day |  |

| Thursday, 13 February Venue: SSI Statens Serum Laboratorium (Artillerivej 5, 2300 Copenhagen S) |  |  |
| --- | --- | --- |
| 9:00 | Re-cap from Wednesday and plan for the day Introduction to EURL WG NGS workshop in March 2020 Updating the guidance plans. GANTT charts for each WP; - WP1 – Develop cross-sectional PT’s - WP2 – Creation of EUROpanelOH - WP3 – Access and sustainability of well-defined microbial reference materials (RM) - WP4 – Risk Assessment | Rene S. Hendriksen, DTU Valeria Michellaci, ISS |
| 11:30 | Plenum discussion | Chair: Mia Torpdahl |
| 12:00 | Lunch – End of day |  |